## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : SPAN TRIDENT
Task Name : All Task
Page 1 of 1
Total Records: 108 Records 1 to 108
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | MEP Consultancy Services | 0 | Tentative | Labour | (L)MEP Consultancy Services | No. | 125497.476 | 5.01 | 628742.35 | 125497.476 | 5.01 | 628742.35 | 0 | 5.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125497.476 | 125497.476 | 628742.355 | 628742.3548
2 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)RMC - M35 | Cum. | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 481 | 0 | 0
3 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 2.8061 | 70.44 | 197.66 | 0 | 0 | 0 | 0 | 70.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8061 | 2.8061 | 197.662 | 197.6617
4 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 1.8174 | 70.44 | 128.02 | 0 | 0 | 0 | 0 | 70.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8174 | 1.8174 | 128.018 | 128.0177
5 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 16.8365 | 60180 | 1013220.57 | 0 | 0 | 0 | 0 | 60180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8365 | 16.8365 | 1013220.57 | 1013220.57
6 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)800 MM Dia Piles Boring | RMT | 888 | 2450 | 2175600 | 888 | 2450 | 2175600 | 0 | 2450 | 0 | 888 | 2301 | 2043288 | 877.7 | 2301 | 2019587.72 | 888 | 10.3 | 2175600 | 156012.28
7 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Chiselling in Rock for Socketing | Hrs | 223.85 | 1180 | 264143 | 223.85 | 1180 | 264143 | 0 | 1180 | 0 | 223.85 | 1180 | 264143 | 223.85 | 1180 | 264143 | 223.85 | 0 | 264143 | 0
8 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Mud Removing Charges | Trip | 137 | 3776 | 517312 | 137 | 3776 | 517312 | 0 | 3776 | 0 | 137 | 3776 | 517312 | 137 | 3776 | 517312 | 137 | 0 | 517312 | 0
9 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)RMC Concrete Charges | RMT | 880 | 354 | 311520 | 880 | 354 | 311520 | 0 | 354 | 0 | 880 | 354 | 311520 | 877.7 | 354 | 310705.8 | 880 | 2.3 | 311520 | 814.2
10 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Shore Piling Work Fabricating, Lifting & Lowering Steel | MT | 21.03 | 6500 | 136695 | 21.03 | 6500 | 136695 | 0 | 6500 | 0 | 21.03 | 6490 | 136484.7 | 21.028 | 6490 | 136471.72 | 21.03 | 0.002 | 136695 | 223.28
11 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Shore Piling Work Mobilization At Site | No. | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 100000 | 41000
12 | Doctor Health Checkup | 0 | Started | Labour | (L)Medical Health Checkup | No. | 4 | 1750 | 7000 | 4 | 1750 | 7000 | 0 | 1750 | 0 | 4 | 1750 | 7000 | 0 | 0 | 0 | 4 | 4 | 7000 | 7000
13 | Pest Control Services | 0 | Started | Labour | (L)Pest Control Anti Larval Spray Treatment | No. | 48 | 1652 | 79296 | 48 | 1652 | 79296 | 0 | 1652 | 0 | 48 | 1652 | 79296 | 12 | 1652 | 19824 | 48 | 36 | 79296 | 59472
14 | Pest Control Services | 0 | Started | Labour | (L)Pest Control Fogging | No. | 48 | 1298 | 62304 | 48 | 1298 | 62304 | 0 | 1298 | 0 | 48 | 1298 | 62304 | 12 | 1298 | 15576 | 48 | 36 | 62304 | 46728
15 | PLINTH PODIUM | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 5 | 5900 | 29500 | 5 | 5900 | 29500 | 0 | 5900 | 0 | 5 | 5859.88 | 29299.4 | 0 | 0 | 0 | 5 | 5 | 29500 | 29500
16 | PLINTH PODIUM | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 8482.595 | 1570.58 | 13322594.06 | 8482.595 | 1570.58 | 13322594.06 | 0 | 1570.58 | 0 | 8482.595 | 1258.81 | 10677994.0801 | 0 | 0 | 0 | 8482.595 | 8482.595 | 13322594.055 | 13322594.0551
17 | UG WATER TANK | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2423.599 | 1570.58 | 3806456.12 | 2423.599 | 1570.58 | 3806456.12 | 0 | 1570.58 | 0 | 2423.599 | 1258.81 | 3050855.9972 | 0 | 0 | 0 | 2423.599 | 2423.599 | 3806456.117 | 3806456.1174
18 | STP | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 1211.799 | 1570.58 | 1903227.27 | 1211.799 | 1570.58 | 1903227.27 | 0 | 1570.58 | 0 | 1211.799 | 1258.81 | 1525427.3752 | 0 | 0 | 0 | 1211.799 | 1211.799 | 1903227.273 | 1903227.2734
19 | 1st SLAB BUILDING | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 1570.58 | 5709683.39 | 0 | 1570.58 | 0 | 3635.398 | 1258.81 | 4576283.3524 | 3635.398 | 1258.81 | 4576283.35 | 3635.398 | 0 | 5709683.391 | 1133400.0408
20 | 1st SLAB PODIUM | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 0 | 5900 | 0 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 3 | 3 | 17700 | 17700
21 | 1st SLAB PODIUM | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
22 | 2nd SLAB BUILDING | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 3029.498 | 1258.81 | 3813569.05 | 3029.498 | 0 | 4758068.969 | 944499.9188
23 | 2nd SLAB PODIUM | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 0 | 5900 | 0 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 3 | 3 | 17700 | 17700
24 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 70.44 | 387.42 | 0 | 70.44 | 0 | 5.5 | 60770 | 334235 | 3 | 60770 | 182310 | 5.5 | 2.5 | 387.42 | -181922.58
25 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 59590 | 59590 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
26 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 70.44 | 176.1 | 0 | 70.44 | 0 | 2.5 | 59590 | 148975 | 1 | 59590 | 59590 | 2.5 | 1.5 | 176.1 | -59413.9
27 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 60180 | 150450 | 0 | 60180 | 0 | 2.5 | 59590 | 148975 | 1 | 59590 | 59590 | 2.5 | 1.5 | 150450 | 90860
28 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 5 | 81.18 | 405.9 | 5 | 81.18 | 405.9 | 0 | 81.18 | 0 | 5 | 60180 | 300900 | 3 | 60180 | 180540 | 5 | 2 | 405.9 | -180134.1
29 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 60180 | 60180 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
30 | 2nd SLAB PODIUM | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
31 | 3rd SLAB | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
32 | 3rd SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
33 | 3rd SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 70.44 | 387.42 | 0 | 70.44 | 0 | 5.5 | 60770 | 334235 | 6.58 | 60770 | 399866.6 | 5.5 | -1.08 | 387.42 | -399479.18
35 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 59590 | 59590 | 1.87 | 59590 | 111433.3 | 1 | -0.87 | 70.44 | -111362.86
36 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 70.44 | 176.1 | 0 | 70.44 | 0 | 2.5 | 59590 | 148975 | 2.5 | 59590 | 148975 | 2.5 | 0 | 176.1 | -148798.9
37 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 60180 | 150450 | 0 | 60180 | 0 | 2.5 | 59590 | 148975 | 1.2 | 59590 | 71508 | 2.5 | 1.3 | 150450 | 78942
38 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 5 | 70.44 | 352.2 | 5 | 70.44 | 352.2 | 0 | 70.44 | 0 | 5 | 60180 | 300900 | 6.449 | 60180 | 388100.82 | 5 | -1.449 | 352.2 | -387748.62
39 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 60180 | 60180 | 1.997 | 60180 | 120179.46 | 1 | -0.997 | 70.44 | -120109.02
40 | 3rd SLAB | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
41 | 4th SLAB | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
42 | 4th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
43 | 4th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 14.5 | 70.44 | 1021.38 | 11.5 | 70.44 | 810.06 | 0 | 70.44 | 0 | 11.5 | 63130 | 725995 | 11.49 | 63130 | 725363.7 | 14.5 | 3.01 | 1021.38 | -724342.32
45 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 0.5 | 70.44 | 35.22 | 0 | 70.44 | 0 | 0.5 | 61950 | 30975 | 0.5 | 61950 | 30975 | 1 | 0.5 | 70.44 | -30904.56
46 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2 | 70.44 | 140.88 | 0.5 | 70.44 | 35.22 | 0 | 70.44 | 0 | 0.5 | 61950 | 30975 | 0.5 | 61950 | 30975 | 2 | 1.5 | 140.88 | -30834.12
47 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 3 | 60180 | 180540 | 3 | 60180 | 180540 | 0 | 60180 | 0 | 3 | 61950 | 185850 | 3 | 61950 | 185850 | 3 | 0 | 180540 | -5310
48 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 13 | 70.44 | 915.72 | 10.5 | 70.44 | 739.62 | 0 | 70.44 | 0 | 10.5 | 62540 | 656670 | 10.54 | 62540 | 659171.6 | 13 | 2.46 | 915.72 | -658255.88
49 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 9 | 70.44 | 633.96 | 9 | 70.44 | 633.96 | 0 | 70.44 | 0 | 9 | 62540 | 562860 | 9.04 | 62540 | 565361.6 | 9 | -0.04 | 633.96 | -564727.64
50 | 4th SLAB | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
51 | 5th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
52 | 5th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
53 | 5th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 5th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
55 | 6th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
56 | 6th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
57 | 6th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 6th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
59 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
60 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
61 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 7th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
63 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 0 | 5900 | 0 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 9 | 9 | 53100 | 53100
64 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
65 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 8th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
67 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
68 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
69 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 9th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
71 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
72 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
73 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 10th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
75 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
76 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
77 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 11th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
79 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
80 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
81 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 12th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
83 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 0 | 5900 | 0 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 9 | 9 | 53100 | 53100
84 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
85 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 13th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
87 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
88 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
89 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 14th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
91 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
92 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
93 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 15th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 1570.58 | 4605810.66 | 0 | 1570.58 | 0 | 2932.554 | 1258.81 | 3691534.7617 | 0 | 0 | 0 | 2932.554 | 2932.554 | 4605810.661 | 4605810.6613
95 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
96 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 2 | 4564 | 9128 | 2 | 4564 | 9128 | 0 | 4564 | 0 | 2 | 5385.52 | 10771.04 | 0 | 0 | 0 | 2 | 2 | 9128 | 9128
97 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 16th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 1570.58 | 4605810.66 | 0 | 1570.58 | 0 | 2932.554 | 1258.81 | 3691534.7617 | 0 | 0 | 0 | 2932.554 | 2932.554 | 4605810.661 | 4605810.6613
99 | BRICK WORK EXTERNAL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
100 | BRICK WORK INTERNAL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
101 | INTERNAL PLASTER | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
102 | EXTERNAL PLASTER | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
103 | PCC COMPOUND WALL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
104 | WATERPROOFING | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 1570.58 | 7612910.66 | 0 | 1570.58 | 0 | 4847.197 | 1258.81 | 6101710.7276 | 0 | 0 | 0 | 4847.197 | 4847.197 | 7612910.664 | 7612910.6643
105 | OVERHEAD TANK AND LMR | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 1570.58 | 5709683.39 | 0 | 1570.58 | 0 | 3635.398 | 1258.81 | 4576283.3524 | 0 | 0 | 0 | 3635.398 | 3635.398 | 5709683.391 | 5709683.3908
106 | Pumping Charges | 0 | Tentative | Labour | (L)Pumping Charges | Cum | 1000 | 472 | 472000 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 472000 | 472000
107 | Machinery and Equipment | 0 | Tentative | Material | (M)Anti Smog Gun | No. | 1 | 413000 | 413000 | 1 | 413000 | 413000 | 0 | 413000 | 0 | 1 | 133300 | 133300 | 0 | 0 | 0 | 1 | 1 | 413000 | 413000
108 | Misc. Handover | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 1570.58 | 7612910.66 | 0 | 1570.58 | 0 | 4847.197 | 1258.81 | 6101710.7276 | 0 | 0 | 0 | 4847.197 | 4847.197 | 7612910.664 | 7612910.6643