## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : SPAN TRIDENT
Task Name : All Task
Page 1 of 1
Total Records: 124 Records 1 to 124
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | MEP Consultancy Services | 0 | Tentative | Labour | (L)MEP Consultancy Services | No. | 125497.476 | 5.01 | 628742.35 | 125497.476 | 5.01 | 628742.35 | 0 | 5.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125497.476 | 125497.476 | 628742.355 | 628742.3548
2 | Doctor Health Checkup | 0 | Started | Labour | (L)Medical Health Checkup | No. | 48 | 1750 | 84000 | 4 | 1750 | 7000 | 0 | 1750 | 0 | 48 | 1750 | 84000 | 6 | 1750 | 10500 | 48 | 42 | 84000 | 73500
3 | Pest Control Services | 0 | Started | Labour | (L)Pest Control Anti Larval Spray Treatment | No. | 48 | 1652 | 79296 | 48 | 1652 | 79296 | 0 | 1652 | 0 | 48 | 1652 | 79296 | 12 | 1652 | 19824 | 48 | 36 | 79296 | 59472
4 | Pest Control Services | 0 | Started | Labour | (L)Pest Control Fogging | No. | 48 | 1298 | 62304 | 48 | 1298 | 62304 | 0 | 1298 | 0 | 48 | 1298 | 62304 | 12 | 1298 | 15576 | 48 | 36 | 62304 | 46728
5 | UG WATER TANK | 0 | Tentative | Material | (M)TMT Bars FE500D 12mm. | MT | 10 | 70.44 | 704.4 | 10 | 70.44 | 704.4 | 0 | 70.44 | 0 | 10 | 62776 | 627760 | 0 | 0 | 0 | 10 | 10 | 704.4 | 704.4
6 | UG WATER TANK | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2423.599 | 1570.58 | 3806456.12 | 2423.599 | 1570.58 | 3806456.12 | 0 | 1570.58 | 0 | 2423.599 | 1258.81 | 3050855.9972 | 0 | 0 | 0 | 2423.599 | 2423.599 | 3806456.117 | 3806456.1174
7 | STP | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 1211.799 | 1570.58 | 1903227.27 | 1211.799 | 1570.58 | 1903227.27 | 0 | 1570.58 | 0 | 1211.799 | 1258.81 | 1525427.3752 | 0 | 0 | 0 | 1211.799 | 1211.799 | 1903227.273 | 1903227.2734
8 | PLINTH PODIUM | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 5 | 5900 | 29500 | 5 | 5900 | 29500 | 0 | 5900 | 0 | 5 | 5859.88 | 29299.4 | 0 | 0 | 0 | 5 | 5 | 29500 | 29500
9 | PLINTH PODIUM | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 8482.595 | 1570.58 | 13322594.06 | 8482.595 | 1570.58 | 13322594.06 | 0 | 1570.58 | 0 | 8482.595 | 1258.81 | 10677994.0801 | 0 | 0 | 0 | 8482.595 | 8482.595 | 13322594.055 | 13322594.0551
10 | 1st SLAB BUILDING | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 1570.58 | 5709683.39 | 0 | 1570.58 | 0 | 3635.398 | 1258.81 | 4576283.3524 | 3635.398 | 1258.81 | 4576283.35 | 3635.398 | 0 | 5709683.391 | 1133400.0408
11 | 1st SLAB PODIUM | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 0 | 5900 | 0 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 3 | 3 | 17700 | 17700
12 | 1st SLAB PODIUM | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
13 | 2nd SLAB BUILDING | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 3029.498 | 1258.81 | 3813569.05 | 3029.498 | 0 | 4758068.969 | 944499.9188
14 | 2nd SLAB PODIUM | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 5900 | 17700 | 0 | 5900 | 0 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 3 | 3 | 17700 | 17700
15 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 70.44 | 387.42 | 0 | 70.44 | 0 | 5.5 | 60770 | 334235 | 3 | 60770 | 182310 | 5.5 | 2.5 | 387.42 | -181922.58
16 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 59590 | 59590 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
17 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 70.44 | 176.1 | 0 | 70.44 | 0 | 2.5 | 59590 | 148975 | 1 | 59590 | 59590 | 2.5 | 1.5 | 176.1 | -59413.9
18 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 60180 | 150450 | 0 | 60180 | 0 | 2.5 | 59590 | 148975 | 1 | 59590 | 59590 | 2.5 | 1.5 | 150450 | 90860
19 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 5 | 81.18 | 405.9 | 5 | 81.18 | 405.9 | 0 | 81.18 | 0 | 5 | 60180 | 300900 | 3 | 60180 | 180540 | 5 | 2 | 405.9 | -180134.1
20 | 2nd SLAB PODIUM | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 60180 | 60180 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
21 | 2nd SLAB PODIUM | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
22 | PCC COMPOUND WALL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 1570.58 | 4758068.97 | 0 | 1570.58 | 0 | 3029.498 | 1258.81 | 3813569.0514 | 0 | 0 | 0 | 3029.498 | 3029.498 | 4758068.969 | 4758068.9688
23 | WATERPROOFING | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 1570.58 | 7612910.66 | 0 | 1570.58 | 0 | 4847.197 | 1258.81 | 6101710.7276 | 0 | 0 | 0 | 4847.197 | 4847.197 | 7612910.664 | 7612910.6643
24 | OVERHEAD TANK AND LMR | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 1570.58 | 5709683.39 | 0 | 1570.58 | 0 | 3635.398 | 1258.81 | 4576283.3524 | 0 | 0 | 0 | 3635.398 | 3635.398 | 5709683.391 | 5709683.3908
25 | 3rd SLAB | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
26 | 3rd SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
27 | 3rd SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 70.44 | 387.42 | 0 | 70.44 | 0 | 5.5 | 60770 | 334235 | 6.58 | 60770 | 399866.6 | 5.5 | -1.08 | 387.42 | -399479.18
29 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 59590 | 59590 | 1.87 | 59590 | 111433.3 | 1 | -0.87 | 70.44 | -111362.86
30 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 70.44 | 176.1 | 0 | 70.44 | 0 | 2.5 | 59590 | 148975 | 2.5 | 59590 | 148975.01 | 2.5 | 0 | 176.1 | -148798.91
31 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 60180 | 150450 | 0 | 60180 | 0 | 2.5 | 59590 | 148975 | 1.2 | 59590 | 71508 | 2.5 | 1.3 | 150450 | 78942
32 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 5 | 70.44 | 352.2 | 5 | 70.44 | 352.2 | 0 | 70.44 | 0 | 5 | 60180 | 300900 | 6.449 | 60180 | 388100.82 | 5 | -1.449 | 352.2 | -387748.62
33 | 3rd SLAB | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 60180 | 60180 | 1.997 | 60180 | 120179.46 | 1 | -0.997 | 70.44 | -120109.02
34 | 3rd SLAB | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 2944.672 | 1258.81 | 3706789.04 | 2944.672 | 0 | 4624842.95 | 918053.9098
35 | 4th SLAB | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
36 | 4th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
37 | 4th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 14.5 | 70.44 | 1021.38 | 11.5 | 70.44 | 810.06 | 0 | 70.44 | 0 | 11.5 | 63130 | 725995 | 11.49 | 63130 | 725363.7 | 14.5 | 3.01 | 1021.38 | -724342.32
39 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 0.5 | 70.44 | 35.22 | 0 | 70.44 | 0 | 0.5 | 61950 | 30975 | 0.5 | 61950 | 30975 | 1 | 0.5 | 70.44 | -30904.56
40 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 2 | 70.44 | 140.88 | 0.5 | 70.44 | 35.22 | 0 | 70.44 | 0 | 0.5 | 61950 | 30975 | 0.5 | 61950 | 30975 | 2 | 1.5 | 140.88 | -30834.12
41 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 3 | 60180 | 180540 | 3 | 60180 | 180540 | 0 | 60180 | 0 | 3 | 61950 | 185850 | 3 | 61950 | 185850 | 3 | 0 | 180540 | -5310
42 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 13 | 70.44 | 915.72 | 10.5 | 70.44 | 739.62 | 0 | 70.44 | 0 | 10.5 | 62540 | 656670 | 10.54 | 62540 | 659171.6 | 13 | 2.46 | 915.72 | -658255.88
43 | 4th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 9 | 70.44 | 633.96 | 9 | 70.44 | 633.96 | 0 | 70.44 | 0 | 9 | 62540 | 562860 | 9.04 | 62540 | 565361.6 | 9 | -0.04 | 633.96 | -564727.64
44 | 4th SLAB | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 2944.672 | 1258.81 | 3706789.04 | 2944.672 | 0 | 4624842.95 | 918053.9098
45 | 5th SLAB | 0 | Started | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
46 | 5th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
47 | 5th SLAB | 0 | Started | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 11 | 70.44 | 774.84 | 11 | 70.44 | 774.84 | 0 | 70.44 | 0 | 11 | 63973.7 | 703710.7 | 10.4 | 63973.7 | 665326.48 | 11 | 0.6 | 774.84 | -664551.64
49 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 10mm. | MT | 0.5 | 70.44 | 35.22 | 0.5 | 70.44 | 35.22 | 0 | 70.44 | 0 | 0.5 | 62793.72 | 31396.86 | 0.54 | 62793.72 | 33908.6088 | 0.5 | -0.04 | 35.22 | -33873.3888
50 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 1.5 | 70.44 | 105.66 | 1.5 | 70.44 | 105.66 | 0 | 70.44 | 0 | 1.5 | 62793.71 | 94190.5601 | 1.52 | 62793.71 | 95446.4392 | 1.5 | -0.02 | 105.66 | -95340.7792
51 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 4.5 | 60180 | 270810 | 4.5 | 60180 | 270810 | 0 | 60180 | 0 | 4.5 | 62793.7 | 282571.6599 | 4.54 | 62793.7 | 285083.398 | 4.5 | -0.04 | 270810 | -14273.398
52 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 20mm. | MT | 9.5 | 70.44 | 669.18 | 9.5 | 70.44 | 669.18 | 0 | 70.44 | 0 | 9.5 | 63383.7 | 602145.1605 | 9.5 | 63383.7 | 602145.15 | 9.5 | 0 | 669.18 | -601475.97
53 | 5th SLAB | 0 | Started | Material | (M)TMT Bars FE500D 25mm. | MT | 8 | 70.44 | 563.52 | 8 | 70.44 | 563.52 | 0 | 70.44 | 0 | 8 | 63383.7 | 507069.6 | 7.52 | 63383.7 | 476645.424 | 8 | 0.48 | 563.52 | -476081.904
54 | 5th SLAB | 0 | Started | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
55 | 6th SLAB | 0 | Confirm | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
56 | 6th SLAB | 0 | Confirm | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
57 | 6th SLAB | 0 | Confirm | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 08mm. | MT | 6.5 | 70.44 | 457.86 | 6.5 | 70.44 | 457.86 | 0 | 70.44 | 0 | 6.5 | 63956 | 415714 | 0 | 0 | 0 | 6.5 | 6.5 | 457.86 | 457.86
59 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 62776 | 62776 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
60 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 12mm. | MT | 1 | 70.44 | 70.44 | 1 | 70.44 | 70.44 | 0 | 70.44 | 0 | 1 | 62776 | 62776 | 0 | 0 | 0 | 1 | 1 | 70.44 | 70.44
61 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 16mm | MT | 2 | 60180 | 120360 | 2 | 60180 | 120360 | 0 | 60180 | 0 | 2 | 62776 | 125552 | 0 | 0 | 0 | 2 | 2 | 120360 | 120360
62 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 20mm. | MT | 9 | 70.44 | 633.96 | 9 | 70.44 | 633.96 | 0 | 70.44 | 0 | 9 | 63366 | 570294 | 0 | 0 | 0 | 9 | 9 | 633.96 | 633.96
63 | 6th SLAB | 0 | Confirm | Material | (M)TMT Bars FE500D 25mm. | MT | 3.5 | 70.44 | 246.54 | 3.5 | 70.44 | 246.54 | 0 | 70.44 | 0 | 3.5 | 63366 | 221781 | 0 | 0 | 0 | 3.5 | 3.5 | 246.54 | 246.54
64 | 6th SLAB | 0 | Confirm | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
65 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
66 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
67 | 7th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 7th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
69 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 0 | 5900 | 0 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 9 | 9 | 53100 | 53100
70 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
71 | 8th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 8th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
73 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
74 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
75 | 9th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 9th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
77 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
78 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
79 | 10th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 10th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
81 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
82 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
83 | 11th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 11th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
85 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
86 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
87 | 12th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 12th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
89 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 5900 | 53100 | 0 | 5900 | 0 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 9 | 9 | 53100 | 53100
90 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
91 | 13th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 13th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
93 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
94 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
95 | 14th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 14th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 1570.58 | 4624842.95 | 0 | 1570.58 | 0 | 2944.672 | 1258.81 | 3706789.0429 | 0 | 0 | 0 | 2944.672 | 2944.672 | 4624842.95 | 4624842.9498
97 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
98 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 4564 | 54768 | 0 | 4564 | 0 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 12 | 12 | 54768 | 54768
99 | 15th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 15th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 1570.58 | 4605810.66 | 0 | 1570.58 | 0 | 2932.554 | 1258.81 | 3691534.7617 | 0 | 0 | 0 | 2932.554 | 2932.554 | 4605810.661 | 4605810.6613
101 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 5900 | 47200 | 0 | 5900 | 0 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 8 | 8 | 47200 | 47200
102 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 2 | 4564 | 9128 | 2 | 4564 | 9128 | 0 | 4564 | 0 | 2 | 5385.52 | 10771.04 | 0 | 0 | 0 | 2 | 2 | 9128 | 9128
103 | 16th SLAB | 0 | Tentative | Material | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 16th SLAB | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 1570.58 | 4605810.66 | 0 | 1570.58 | 0 | 2932.554 | 1258.81 | 3691534.7617 | 0 | 0 | 0 | 2932.554 | 2932.554 | 4605810.661 | 4605810.6613
105 | BRICK WORK EXTERNAL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
106 | BRICK WORK INTERNAL | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
107 | INTERNAL PLASTER | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
108 | EXTERNAL PLASTER | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 1570.58 | 15225821.33 | 0 | 1570.58 | 0 | 9694.394 | 1258.81 | 12203421.4353 | 0 | 0 | 0 | 9694.394 | 9694.394 | 15225821.329 | 15225821.3285
109 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)RMC - M35 | Cum. | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 481 | 0 | 0
110 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 08mm. | MT | 2.8061 | 70.44 | 197.66 | 0 | 0 | 0 | 0 | 70.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8061 | 2.8061 | 197.662 | 197.6617
111 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 12mm. | MT | 1.8174 | 70.44 | 128.02 | 0 | 0 | 0 | 0 | 70.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8174 | 1.8174 | 128.018 | 128.0177
112 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Material | (M)TMT Bars FE500D 16mm | MT | 16.8365 | 60180 | 1013220.57 | 0 | 0 | 0 | 0 | 60180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8365 | 16.8365 | 1013220.57 | 1013220.57
113 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)800 MM Dia Piles Boring | RMT | 888 | 2450 | 2175600 | 888 | 2450 | 2175600 | 0 | 2450 | 0 | 888 | 2301 | 2043288 | 877.7 | 2301 | 2019587.72 | 888 | 10.3 | 2175600 | 156012.28
114 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Chiselling in Rock for Socketing | Hrs | 223.85 | 1180 | 264143 | 223.85 | 1180 | 264143 | 0 | 1180 | 0 | 223.85 | 1180 | 264143 | 223.85 | 1180 | 264143 | 223.85 | 0 | 264143 | 0
115 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Mud Removing Charges | Trip | 137 | 3776 | 517312 | 137 | 3776 | 517312 | 0 | 3776 | 0 | 137 | 3776 | 517312 | 137 | 3776 | 517312 | 137 | 0 | 517312 | 0
116 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)RMC Concrete Charges | RMT | 880 | 354 | 311520 | 880 | 354 | 311520 | 0 | 354 | 0 | 880 | 354 | 311520 | 877.7 | 354 | 310705.8 | 880 | 2.3 | 311520 | 814.2
117 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Shore Piling Work Fabricating, Lifting & Lowering Steel | MT | 21.03 | 6500 | 136695 | 21.03 | 6500 | 136695 | 0 | 6500 | 0 | 21.03 | 6490 | 136484.7 | 21.028 | 6490 | 136471.72 | 21.03 | 0.002 | 136695 | 223.28
118 | SHORE PILING WORK 800 MM Dia. 24 mtr | 0 | Started | Labour | (L)Shore Piling Work Mobilization At Site | No. | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 59000 | 59000 | 1 | 59000 | 59000 | 1 | 0 | 100000 | 41000
119 | PILE CAP WORK | 0 | Tentative | Material | (M)CONCRETE - M35 | Cu. Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | PILE CAP WORK | 0 | Tentative | Material | (M)CONCRETE - M40 | Cu. Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | PILE CAP WORK | 0 | Tentative | Material | (M)TMT Bars FE500D 20mm. | MT | 2 | 70.44 | 140.88 | 2 | 70.44 | 140.88 | 0 | 70.44 | 0 | 2 | 63366 | 126732 | 0 | 0 | 0 | 2 | 2 | 140.88 | 140.88
122 | Machinery and Equipment | 0 | Tentative | Material | (M)Anti Smog Gun | No. | 1 | 413000 | 413000 | 1 | 413000 | 413000 | 0 | 413000 | 0 | 1 | 133300 | 133300 | 0 | 0 | 0 | 1 | 1 | 413000 | 413000
123 | Pumping Charges | 0 | Tentative | Labour | (L)Pumping Charges | Cum | 1000 | 472 | 472000 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 472000 | 472000
124 | Misc. Handover | 0 | Tentative | Labour | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 1570.58 | 7612910.66 | 0 | 1570.58 | 0 | 4847.197 | 1258.81 | 6101710.7276 | 0 | 0 | 0 | 4847.197 | 4847.197 | 7612910.664 | 7612910.6643