## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : SPAN TRIDENT
Task Name : All Task
Page 1 of 1
Total Records: 124 Records 1 to 124
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Name | Task_QTY | Task_QTY_UNIT
1 | CEMENT CONCRETE | (M)CONCRETE - M35 | Cu. Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PILE CAP WORK | 0 | Mtr
2 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 10th SLAB | 1
3 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 11th SLAB | 1
4 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 12th SLAB | 1
5 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 0 | 0 | 9 | 361.08 | 53100 | 13th SLAB | 1
6 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 14th SLAB | 1
7 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 15th SLAB | 1
8 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 16th SLAB | 1
9 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 0 | 0 | 3 | 120.36 | 17700 | 1st SLAB PODIUM | 1
10 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 3 | 5900 | 17700 | 3 | 3 | 5859.88 | 17579.64 | 0 | 0 | 0 | 0 | 0 | 3 | 120.36 | 17700 | 2nd SLAB PODIUM | 1
11 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 3rd SLAB | 1
12 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 4th SLAB | 1
13 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 5th SLAB | 1
14 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 6th SLAB | 1
15 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 7th SLAB | 1
16 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 9 | 5900 | 53100 | 9 | 9 | 5859.88 | 52738.92 | 0 | 0 | 0 | 0 | 0 | 9 | 361.08 | 53100 | 8th SLAB | 1
17 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 8 | 5900 | 47200 | 8 | 8 | 5859.88 | 46879.04 | 0 | 0 | 0 | 0 | 0 | 8 | 320.96 | 47200 | 9th SLAB | 1
18 | DOORS & WINDOWS | (M)Door frame 1000mmx2450mm section 40mmx140mm | No. | 5 | 5900 | 29500 | 5 | 5 | 5859.88 | 29299.4 | 0 | 0 | 0 | 0 | 0 | 5 | 200.6 | 29500 | PLINTH PODIUM | 1
19 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10th SLAB | 1
20 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11th SLAB | 1
21 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12th SLAB | 1
22 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13th SLAB | 1
23 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14th SLAB | 1
24 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15th SLAB | 1
25 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16th SLAB | 1
26 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3rd SLAB | 1
27 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4th SLAB | 1
28 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5th SLAB | 1
29 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6th SLAB | 1
30 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7th SLAB | 1
31 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8th SLAB | 1
32 | DOORS & WINDOWS | (M)Door frame 900mmx2450mm section 40mmx120mm | No. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9th SLAB | 1
33 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 10th SLAB | 1
34 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 11th SLAB | 1
35 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 12th SLAB | 1
36 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 13th SLAB | 1
37 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 14th SLAB | 1
38 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 15th SLAB | 1
39 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 2 | 4564 | 9128 | 2 | 2 | 5385.52 | 10771.04 | 0 | 0 | 0 | 0 | 0 | 2 | -1643.04 | 9128 | 16th SLAB | 1
40 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 3rd SLAB | 1
41 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 4th SLAB | 1
42 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 5th SLAB | 1
43 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 6th SLAB | 1
44 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 7th SLAB | 1
45 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 8th SLAB | 1
46 | DOORS/ WINDOWS | (M)Door frame 900mmx2450mm section 40mmx100mm | No. | 12 | 4564 | 54768 | 12 | 12 | 5385.52 | 64626.24 | 0 | 0 | 0 | 0 | 0 | 12 | -9858.24 | 54768 | 9th SLAB | 1
47 | ELECTRICAL MATERIAL | (M)Anti Smog Gun | No. | 1 | 413000 | 413000 | 1 | 1 | 133300 | 133300 | 1 | 0 | 0 | 0 | 0 | 1 | 279700 | 413000 | Machinery and Equipment | 1 | Rft
48 | READY MIX CONCRETE | (M)CONCRETE - M40 | Cu. Mtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PILE CAP WORK | 0 | Mtr
49 | RMC | (M)RMC - M35 | Cum. | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 481 | 0 | 0 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
50 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 5.5 | 60770 | 334235 | 4.08 | 3 | 60770 | 182310 | 0 | 2.5 | -333847.58 | -181922.58 | 2nd SLAB PODIUM | 1
51 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 5.5 | 70.44 | 387.42 | 5.5 | 5.5 | 60770 | 334235 | 5.5 | 6.58 | 60770 | 399866.6 | 0 | -1.08 | -333847.58 | -399479.18 | 3rd SLAB | 1
52 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 14.5 | 70.44 | 1021.38 | 11.5 | 11.5 | 63130 | 725995 | 11.49 | 11.49 | 63130 | 725363.7 | 3 | 3.01 | -724973.62 | -724342.32 | 4th SLAB | 1
53 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 11 | 70.44 | 774.84 | 11 | 11 | 63973.7 | 703710.7 | 10.4 | 10.4 | 63973.7 | 665326.48 | 0 | 0.6 | -702935.86 | -664551.64 | 5th SLAB | 1
54 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 6.5 | 70.44 | 457.86 | 6.5 | 6.5 | 63956 | 415714 | 6.5 | 0 | 0 | 0 | 0 | 6.5 | -415256.14 | 457.86 | 6th SLAB | 1
55 | Structural Steel | (M)TMT Bars FE500D 08mm. | MT | 2.8061 | 70.44 | 197.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8061 | 2.8061 | 197.66 | 197.66 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
56 | Structural Steel | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 59590 | 59590 | 0.87 | 0 | 0 | 0 | 0 | 1 | -59519.56 | 70.44 | 2nd SLAB PODIUM | 1
57 | Structural Steel | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 59590 | 59590 | 1 | 1.87 | 59590 | 111433.3 | 0 | -0.87 | -59519.56 | -111362.86 | 3rd SLAB | 1
58 | Structural Steel | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 0.5 | 0.5 | 61950 | 30975 | 0.5 | 0.5 | 61950 | 30975 | 0.5 | 0.5 | -30904.56 | -30904.56 | 4th SLAB | 1
59 | Structural Steel | (M)TMT Bars FE500D 10mm. | MT | 0.5 | 70.44 | 35.22 | 0.5 | 0.5 | 62793.72 | 31396.86 | 0.5 | 0.54 | 62793.72 | 33908.61 | 0 | -0.04 | -31361.64 | -33873.39 | 5th SLAB | 1
60 | Structural Steel | (M)TMT Bars FE500D 10mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 62776 | 62776 | 1 | 0 | 0 | 0 | 0 | 1 | -62705.56 | 70.44 | 6th SLAB | 1
61 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 2.5 | 59590 | 148975 | 1.697 | 1 | 59590 | 59590 | 0 | 1.5 | -148798.9 | -59413.9 | 2nd SLAB PODIUM | 1
62 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 2.5 | 70.44 | 176.1 | 2.5 | 2.5 | 59590 | 148975 | 2.5 | 2.5 | 59590 | 148975.01 | 0 | 0 | -148798.9 | -148798.91 | 3rd SLAB | 1
63 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 2 | 70.44 | 140.88 | 0.5 | 0.5 | 61950 | 30975 | 0.5 | 0.5 | 61950 | 30975 | 1.5 | 1.5 | -30834.12 | -30834.12 | 4th SLAB | 1
64 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 1.5 | 70.44 | 105.66 | 1.5 | 1.5 | 62793.71 | 94190.56 | 1.5 | 1.52 | 62793.71 | 95446.44 | 0 | -0.02 | -94084.9 | -95340.78 | 5th SLAB | 1
65 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 62776 | 62776 | 1 | 0 | 0 | 0 | 0 | 1 | -62705.56 | 70.44 | 6th SLAB | 1
66 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 1.8174 | 70.44 | 128.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8174 | 1.8174 | 128.02 | 128.02 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
67 | Structural Steel | (M)TMT Bars FE500D 12mm. | MT | 10 | 70.44 | 704.4 | 10 | 10 | 62776 | 627760 | 10 | 0 | 0 | 0 | 0 | 10 | -627055.6 | 704.4 | UG WATER TANK | 1
68 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 2.5 | 59590 | 148975 | 2.29 | 1 | 59590 | 59590 | 0 | 1.5 | 1475 | 90860 | 2nd SLAB PODIUM | 1
69 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 2.5 | 60180 | 150450 | 2.5 | 2.5 | 59590 | 148975 | 2.5 | 1.2 | 59590 | 71508 | 0 | 1.3 | 1475 | 78942 | 3rd SLAB | 1
70 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 3 | 60180 | 180540 | 3 | 3 | 61950 | 185850 | 3 | 3 | 61950 | 185850 | 0 | 0 | -5310 | -5310 | 4th SLAB | 1
71 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 4.5 | 60180 | 270810 | 4.5 | 4.5 | 62793.7 | 282571.66 | 4.5 | 4.54 | 62793.7 | 285083.4 | 0 | -0.04 | -11761.66 | -14273.4 | 5th SLAB | 1
72 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 2 | 60180 | 120360 | 2 | 2 | 62776 | 125552 | 2 | 0 | 0 | 0 | 0 | 2 | -5192 | 120360 | 6th SLAB | 1
73 | Structural Steel | (M)TMT Bars FE500D 16mm | MT | 16.8365 | 60180 | 1013220.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8365 | 16.8365 | 1013220.57 | 1013220.57 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
74 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 5 | 81.18 | 405.9 | 5 | 5 | 60180 | 300900 | 4.449 | 3 | 60180 | 180540 | 0 | 2 | -300494.1 | -180134.1 | 2nd SLAB PODIUM | 1
75 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 5 | 70.44 | 352.2 | 5 | 5 | 60180 | 300900 | 5 | 6.449 | 60180 | 388100.82 | 0 | -1.449 | -300547.8 | -387748.62 | 3rd SLAB | 1
76 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 13 | 70.44 | 915.72 | 10.5 | 10.5 | 62540 | 656670 | 10.5 | 10.54 | 62540 | 659171.6 | 2.5 | 2.46 | -655754.28 | -658255.88 | 4th SLAB | 1
77 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 9.5 | 70.44 | 669.18 | 9.5 | 9.5 | 63383.7 | 602145.16 | 9.5 | 9.5 | 63383.7 | 602145.15 | 0 | 0 | -601475.98 | -601475.97 | 5th SLAB | 1
78 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 9 | 70.44 | 633.96 | 9 | 9 | 63366 | 570294 | 9 | 0 | 0 | 0 | 0 | 9 | -569660.04 | 633.96 | 6th SLAB | 1
79 | STRUCTURAL STEEL | (M)TMT Bars FE500D 20mm. | MT | 2 | 70.44 | 140.88 | 2 | 2 | 63366 | 126732 | 2 | 0 | 0 | 0 | 0 | 2 | -126591.12 | 140.88 | PILE CAP WORK | 0 | Mtr
80 | Structural Steel | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 60180 | 60180 | 0.997 | 0 | 0 | 0 | 0 | 1 | -60109.56 | 70.44 | 2nd SLAB PODIUM | 1
81 | Structural Steel | (M)TMT Bars FE500D 25mm. | MT | 1 | 70.44 | 70.44 | 1 | 1 | 60180 | 60180 | 1 | 1.997 | 60180 | 120179.46 | 0 | -0.997 | -60109.56 | -120109.02 | 3rd SLAB | 1
82 | Structural Steel | (M)TMT Bars FE500D 25mm. | MT | 9 | 70.44 | 633.96 | 9 | 9 | 62540 | 562860 | 9 | 9.04 | 62540 | 565361.6 | 0 | -0.04 | -562226.04 | -564727.64 | 4th SLAB | 1
83 | Structural Steel | (M)TMT Bars FE500D 25mm. | MT | 8 | 70.44 | 563.52 | 8 | 8 | 63383.7 | 507069.6 | 7.52 | 7.52 | 63383.7 | 476645.42 | 0 | 0.48 | -506506.08 | -476081.9 | 5th SLAB | 1
84 | Structural Steel | (M)TMT Bars FE500D 25mm. | MT | 3.5 | 70.44 | 246.54 | 3.5 | 3.5 | 63366 | 221781 | 3.5 | 0 | 0 | 0 | 0 | 3.5 | -221534.46 | 246.54 | 6th SLAB | 1
85 |  | (L)Shore Piling Work Fabricating, Lifting & Lowering Steel | MT | 21.03 | 6500 | 136695 | 21.03 | 21.03 | 6490 | 136484.7 | 21.028 | 21.028 | 6490 | 136471.72 | 0 | 0.002 | 210.3 | 223.28 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
86 |  | (L)Shore Piling Work Mobilization At Site | No. | 1 | 100000 | 100000 | 1 | 1 | 59000 | 59000 | 1 | 1 | 59000 | 59000 | 0 | 0 | 41000 | 41000 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
87 | Consultancy | (L)MEP Consultancy Services | No. | 125497.476 | 5.01 | 628742.35 | 125497.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125497.476 | 125497.476 | 628742.35 | 628742.35 | MEP Consultancy Services | 125497.476
88 | Excavation | (L)800 MM Dia Piles Boring | RMT | 888 | 2450 | 2175600 | 888 | 888 | 2301 | 2043288 | 877.7 | 877.7 | 2301 | 2019587.72 | 0 | 10.3 | 132312 | 156012.28 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
89 | Excavation | (L)Chiselling in Rock for Socketing | Hrs | 223.85 | 1180 | 264143 | 223.85 | 223.85 | 1180 | 264143 | 223.85 | 223.85 | 1180 | 264143 | 0 | 0 | 0 | 0 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
90 | Excavation | (L)Mud Removing Charges | Trip | 137 | 3776 | 517312 | 137 | 137 | 3776 | 517312 | 137 | 137 | 3776 | 517312 | 0 | 0 | 0 | 0 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
91 | Excavation | (L)RMC Concrete Charges | RMT | 880 | 354 | 311520 | 880 | 880 | 354 | 311520 | 877.7 | 877.7 | 354 | 310705.8 | 0 | 2.3 | 0 | 814.2 | SHORE PILING WORK 800 MM Dia. 24 mtr | 1
92 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 10th SLAB | 1
93 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 11th SLAB | 1
94 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 12th SLAB | 1
95 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 13th SLAB | 1
96 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 14th SLAB | 1
97 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 2932.554 | 1258.81 | 3691534.76 | 0 | 0 | 0 | 0 | 0 | 2932.554 | 914275.9 | 4605810.66 | 15th SLAB | 1
98 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1570.58 | 4605810.66 | 2932.554 | 2932.554 | 1258.81 | 3691534.76 | 0 | 0 | 0 | 0 | 0 | 2932.554 | 914275.9 | 4605810.66 | 16th SLAB | 1
99 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 3635.398 | 1258.81 | 4576283.35 | 3635.398 | 3635.398 | 1258.81 | 4576283.35 | 0 | 0 | 1133400.04 | 1133400.04 | 1st SLAB BUILDING | 1
100 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 3029.498 | 1258.81 | 3813569.05 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 944499.92 | 4758068.97 | 1st SLAB PODIUM | 1
101 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 3029.498 | 1258.81 | 3813569.05 | 3029.498 | 3029.498 | 1258.81 | 3813569.05 | 0 | 0 | 944499.92 | 944499.92 | 2nd SLAB BUILDING | 1
102 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 3029.498 | 1258.81 | 3813569.05 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 944499.92 | 4758068.97 | 2nd SLAB PODIUM | 1
103 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 918053.91 | 918053.91 | 3rd SLAB | 1
104 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 918053.91 | 918053.91 | 4th SLAB | 1
105 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 5th SLAB | 1
106 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 6th SLAB | 1
107 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 7th SLAB | 1
108 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 8th SLAB | 1
109 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1570.58 | 4624842.95 | 2944.672 | 2944.672 | 1258.81 | 3706789.04 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 918053.91 | 4624842.95 | 9th SLAB | 1
110 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 9694.394 | 1258.81 | 12203421.44 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 3022399.89 | 15225821.33 | BRICK WORK EXTERNAL | 1
111 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 9694.394 | 1258.81 | 12203421.44 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 3022399.89 | 15225821.33 | BRICK WORK INTERNAL | 1
112 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 9694.394 | 1258.81 | 12203421.44 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 3022399.89 | 15225821.33 | EXTERNAL PLASTER | 1
113 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1570.58 | 15225821.33 | 9694.394 | 9694.394 | 1258.81 | 12203421.44 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 3022399.89 | 15225821.33 | INTERNAL PLASTER | 1
114 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 4847.197 | 1258.81 | 6101710.73 | 0 | 0 | 0 | 0 | 0 | 4847.197 | 1511199.94 | 7612910.66 | Misc. Handover | 1 | Rft
115 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1570.58 | 5709683.39 | 3635.398 | 3635.398 | 1258.81 | 4576283.35 | 0 | 0 | 0 | 0 | 0 | 3635.398 | 1133400.04 | 5709683.39 | OVERHEAD TANK AND LMR | 1
116 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1570.58 | 4758068.97 | 3029.498 | 3029.498 | 1258.81 | 3813569.05 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 944499.92 | 4758068.97 | PCC COMPOUND WALL | 1
117 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 8482.595 | 1570.58 | 13322594.06 | 8482.595 | 8482.595 | 1258.81 | 10677994.08 | 0 | 0 | 0 | 0 | 0 | 8482.595 | 2644599.98 | 13322594.06 | PLINTH PODIUM | 1
118 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 1211.799 | 1570.58 | 1903227.27 | 1211.799 | 1211.799 | 1258.81 | 1525427.38 | 0 | 0 | 0 | 0 | 0 | 1211.799 | 377799.9 | 1903227.27 | STP | 1
119 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 2423.599 | 1570.58 | 3806456.12 | 2423.599 | 2423.599 | 1258.81 | 3050856 | 0 | 0 | 0 | 0 | 0 | 2423.599 | 755600.12 | 3806456.12 | UG WATER TANK | 1
120 | RCC | (L)Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1570.58 | 7612910.66 | 4847.197 | 4847.197 | 1258.81 | 6101710.73 | 0 | 0 | 0 | 0 | 0 | 4847.197 | 1511199.94 | 7612910.66 | WATERPROOFING | 1
121 | RCC | (L)Pumping Charges | Cum | 1000 | 472 | 472000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 472000 | 472000 | Pumping Charges | 1 | Mtr
122 | Services | (L)Medical Health Checkup | No. | 48 | 1750 | 84000 | 4 | 48 | 1750 | 84000 | 6 | 6 | 1750 | 10500 | 0 | 42 | 0 | 73500 | Doctor Health Checkup | 1 | Rft
123 | Services | (L)Pest Control Anti Larval Spray Treatment | No. | 48 | 1652 | 79296 | 48 | 48 | 1652 | 79296 | 12 | 12 | 1652 | 19824 | 0 | 36 | 0 | 59472 | Pest Control Services | 1 | Rft
124 | Services | (L)Pest Control Fogging | No. | 48 | 1298 | 62304 | 48 | 48 | 1298 | 62304 | 12 | 12 | 1298 | 15576 | 0 | 36 | 0 | 46728 | Pest Control Services | 1 | Rft