## Requisition_Tracking-Summary638
Requistion Tracking - Summary
From Date : 08/12/2023 To date: 08/01/2025
Page 1 of 1
Total Records: 30 Records 1 to 30
Project | Task_Name | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | Balance_To_Approve_Qty | Balance_To_Order_Qty | User_Name | Status | Remark
SPAN TRIDENT |  | Steel 08mm | Metric Ton | 1206 | 11 Dec 2024 | 18 Dec 2024 | 10 | 10 | 10 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | Steel 10mm | Metric Ton | 1207 | 11 Dec 2024 | 18 Dec 2024 | 1 | 1 | 1 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | Steel 20mm | Metric Ton | 1208 | 11 Dec 2024 | 18 Dec 2024 | 16 | 16 | 16 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | Steel 25mm | Metric Ton | 1209 | 11 Dec 2024 | 18 Dec 2024 | 8 | 8 | 8 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500 8mm | MT | 1239 | 04 Jan 2025 | 11 Jan 2025 | 11 | 11 | 11 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500 10mm | MT | 1240 | 04 Jan 2025 | 11 Jan 2025 | 2 | 2 | 2 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500D 12mm | Kg | 1241 | 04 Jan 2025 | 11 Jan 2025 | 5 | 5 | 5 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500 20mm | MT | 1242 | 04 Jan 2025 | 11 Jan 2025 | 10 | 10 | 10 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500D 25mm | Kg | 1243 | 04 Jan 2025 | 11 Jan 2025 | 2 | 2 | 2 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500D 16mm | MT | 1244 | 04 Jan 2025 | 11 Jan 2025 | 5 | 5 | 5 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT BAR FE-500 8MM | MT | 1245 | 07 Jan 2025 | 14 Jan 2025 | 11 | 11 | 11 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT BAR FE-500 10MM | MT | 1246 | 07 Jan 2025 | 14 Jan 2025 | 2 | 2 | 2 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500 12mm | MT | 1247 | 07 Jan 2025 | 14 Jan 2025 | 5 | 5 | 5 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT BAR FE-500 16MM | MT | 1248 | 07 Jan 2025 | 14 Jan 2025 | 5 | 5 | 5 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500 20mm | MT | 1249 | 07 Jan 2025 | 14 Jan 2025 | 10 | 10 | 10 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT |  | TMT Bars FE500D 25mm. | MT | 1250 | 07 Jan 2025 | 14 Jan 2025 | 2 | 2 | 2 | 0 | 0 | Nimesh.Makwana | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 08mm. | MT | 1251 | 07 Jan 2025 | 07 Jan 2025 | 5.5 | 5.5 | 5.5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 08mm. | MT | 1252 | 07 Jan 2025 | 07 Jan 2025 | 5.5 | 5.5 | 5.5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 10mm. | MT | 1253 | 07 Jan 2025 | 07 Jan 2025 | 1 | 1 | 1 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 10mm. | MT | 1254 | 07 Jan 2025 | 07 Jan 2025 | 1 | 1 | 1 | 0 | 0 | admin | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 12mm. | MT | 1255 | 07 Jan 2025 | 07 Jan 2025 | 2.5 | 2.5 | 2.5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 12mm. | MT | 1256 | 07 Jan 2025 | 07 Jan 2025 | 2.5 | 2.5 | 2.5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 20mm. | MT | 1257 | 07 Jan 2025 | 07 Jan 2025 | 5 | 5 | 5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 20mm. | MT | 1258 | 07 Jan 2025 | 07 Jan 2025 | 5 | 5 | 5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 25mm. | MT | 1259 | 07 Jan 2025 | 07 Jan 2025 | 1 | 1 | 1 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 25mm. | MT | 1260 | 07 Jan 2025 | 07 Jan 2025 | 1 | 1 | 1 | 0 | 0 | admin | Completed
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 16mm | MT | 1261 | 07 Jan 2025 | 07 Jan 2025 | 0 | 0 | 0 | 0 | 0 | admin | Deleted
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 16mm | MT | 1262 | 07 Jan 2025 | 07 Jan 2025 | 0 | 0 | 0 | 0 | 0 | admin | Deleted
SPAN TRIDENT | 2nd SLAB PODIUM | TMT Bars FE500D 16mm | MT | 1263 | 07 Jan 2025 | 07 Jan 2025 | 2.5 | 2.5 | 2.5 | 0 | 0 | admin | Completed
SPAN TRIDENT | 3rd SLAB | TMT Bars FE500D 16mm | MT | 1264 | 07 Jan 2025 | 07 Jan 2025 | 2.5 | 2.5 | 2.5 | 0 | 0 | admin | Completed