## 638687462099266667_00001.xlsx
RA Bill Payment Date Tracking
Bill Date From : 12/11/2000 To : 03/12/2024
Page 1 of 1
Total Records: 4 Records 1 to 4
Project | Contractor | Bill_No | Planed_Date | Actual_Date | Bill_Date | Site_Inward_Date | Office_Inward_Date | Approved in Contracts | Approved in Accounts | First Payment Date | Last Payment Date | Delay By Contractor | Delay At Site | Delay At Contracts | Delay At Accounts | Total Delay For Task | Total Delay For Billing
SUMIT GURUKRISHNA | JAMUNA CONSTRUCTION SERVICES | 1 | 1900-01-01 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-25 | 2024-10-01 19:00 | 1900-01-01 | 1900-01-01 | 1900-01-01 | 0 | 6 | -190 | 0 | 0 | 0
SUMIT GURUKRISHNA | JAMUNA CONSTRUCTION SERVICES | 2 | 1900-01-01 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-04-10 | 2024-10-03 13:08 | 1900-01-01 | 1900-01-01 | 1900-01-01 | 0 | 0 | -176 | 0 | 0 | 0
SUMIT GURUKRISHNA | PARAMOUNT EDIFICE LLP | 1 | 1900-01-01 | 1900-01-01 | 2023-11-22 12:56 | 2023-11-22 | 2023-11-22 | 2023-11-23 16:35 | 2023-11-23 17:10 | 1900-01-01 | 1900-01-01 | 0 | 0 | -1 | 0 | 0 | 0
SUMIT GURUKRISHNA | SARFARAZ KHAN | 1 | 1900-01-01 | 1900-01-01 | 2023-12-01 16:07 | 2023-12-01 | 2023-12-01 | 2023-12-04 15:13 | 2023-12-04 15:21 | 1900-01-01 | 1900-01-01 | 0 | 0 | -3 | 0 | 0 | 0