## 638799064425107952_00001.xlsx
RA Bill Payment Date Tracking
Bill Date From : 21/03/2000 To : 11/04/2025
Page 1 of 1
Total Records: 7 Records 1 to 7
Project | Contractor | Bill_No | Planed_Date | Actual_Date | Bill_Date | Site_Inward_Date | Office_Inward_Date | Approved in Contracts | Approved in Accounts | First Payment Date | Last Payment Date | Delay By Contractor | Delay At Site | Delay At Contracts | Delay At Accounts | Total Delay For Task | Total Delay For Billing
SPAN TRIDENT | Classic City Pest Control Private Limited | 4 | 1900-01-01 | 2025-01-05 | 2025-02-03 | 2025-01-05 | 2025-01-31 | 2025-02-03 15:41 | 2025-02-24 12:39 | 1900-01-01 | 1900-01-01 | -29 | 26 | -3 | 0 | 0 | 0
SPAN TRIDENT | Harshleen Enterprise LLP | 6 | 1900-01-01 | 2024-12-18 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 16:49 | 2025-02-24 12:36 | 1900-01-01 | 1900-01-01 | -65 | 0 | 0 | 0 | 0 | 0
SPAN TRIDENT | Harshleen Enterprise LLP | 7 | 1900-01-01 | 2025-01-13 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 16:55 | 2025-02-24 12:40 | 1900-01-01 | 1900-01-01 | -39 | 0 | 0 | 0 | 0 | 0
SPAN TRIDENT | KASTUREE ASSOCIATES | 5 | 1900-01-01 | 1900-01-01 | 2025-02-05 | 2025-01-29 | 2025-02-05 | 2025-04-01 18:27 | 2025-04-07 17:16 | 1900-01-01 | 1900-01-01 | 0 | 7 | -55 | 0 | 0 | 0
SPAN TRIDENT | KASTUREE ASSOCIATES | 10 | 1900-01-01 | 2025-03-26 | 2025-04-07 | 2025-03-26 | 2025-03-26 | 2025-04-07 17:09 | 1900-01-01 | 1900-01-01 | 1900-01-01 | -12 | 0 | -12 | 0 | 0 | 0
SPAN TRIDENT | Shri Krishna Clinic | 8 | 1900-01-01 | 2025-02-04 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-26 12:09 | 2025-03-31 15:55 | 1900-01-01 | 1900-01-01 | -49 | 0 | -1 | 0 | 0 | 0
SPAN TRIDENT | Shri Krishna Clinic | 9 | 1900-01-01 | 2025-03-15 | 2025-04-07 | 2025-03-15 | 2025-03-15 | 2025-04-07 16:53 | 1900-01-01 | 2025-04-07 | 2025-04-07 | -23 | 0 | -23 | 0 | 0 | -23