## Project_Work_Order6387990627974
Project Work Order
From 11 Mar 2000 To 11 Apr 2025
Page 1 of 1
Total Records: 68 Records 1 To 68
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
SPAN TRIDENT | 1 | 0 | 21 Dec 2024 | Shri Krishna Clinic | Doctor Health Checkup | Medical Health Checkup | No. | 4 | 1750 | 7000 | 0 | 7000 | 0 | 4 | 7000 | 0 | 0 | 0 | 7000 | 0 | 0 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Consultancy | 21 Dec 2024 |  | Services | Approved | Nimesh.Makwana |  | 100
SPAN TRIDENT | 1 | 0 | 21 Dec 2024 | Shri Krishna Clinic | Doctor Health Checkup | Medical Health Checkup | No. | 44 | 1750 | 77000 | 0 | 77000 | 0 | 2 | 3500 | 0 | 0 | 0 | 3500 | 42 | 73500 |  |  |  | admin | admin | Consultancy | 21 Dec 2024 |  | Services | Approved | admin |  | 4.5455
SPAN TRIDENT | 2 | 0 | 21 Dec 2024 | Classic City Pest Control Private Limited | Pest Control Services | Pest Control Anti Larval Spray Treatment | No. | 48 | 1400 | 67200 | 12096 | 79296 | 0 | 12 | 16800 | 0 | 0 | 3024 | 19824 | 36 | 59472 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Job Work | 21 Dec 2024 |  | Services | Approved | Nimesh.Makwana |  | 25
SPAN TRIDENT | 2 | 0 | 21 Dec 2024 | Classic City Pest Control Private Limited | Pest Control Services | Pest Control Fogging | No. | 48 | 1100 | 52800 | 9504 | 62304 | 0 | 12 | 13200 | 0 | 0 | 2376 | 15576 | 36 | 46728 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Job Work | 21 Dec 2024 |  | Services | Approved | Nimesh.Makwana |  | 25
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 1st SLAB BUILDING | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 1st SLAB PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | PLINTH PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | STP | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | Misc. Handover | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | INTERNAL PLASTER | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | EXTERNAL PLASTER | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | PCC COMPOUND WALL | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | WATERPROOFING | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | OVERHEAD TANK AND LMR | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | UG WATER TANK | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 13th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 14th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 15th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 16th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | BRICK WORK EXTERNAL | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | BRICK WORK INTERNAL | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 7th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 8th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 9th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 10th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 11th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 12th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 2nd SLAB BUILDING | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 2nd SLAB PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 3rd SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 4th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 5th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 3 | 0 | 28 Jan 2025 | KASTUREE ASSOCIATES | 6th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 0 | 1066.67 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Nimesh.Makwana |  | Construction | 29 Jan 2025 |  | RCC | Cancelled | Nimesh.Makwana | 29 Jan 2025 | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | EXTERNAL PLASTER | Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1066.79 | 10341882.58 | 1861538.86 | 12203421.44 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | PCC COMPOUND WALL | Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1066.79 | 3231838.17 | 581730.88 | 3813569.05 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | WATERPROOFING | Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1066.79 | 5170941.29 | 930769.44 | 6101710.73 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4847.197 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | OVERHEAD TANK AND LMR | Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1066.79 | 3878206.23 | 698077.12 | 4576283.35 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3635.398 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | UG WATER TANK | Labours for CIVIL-RCC Work | Sq.ft | 2423.599 | 1066.79 | 2585471.18 | 465384.82 | 3050856 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2423.599 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | STP | Labours for CIVIL-RCC Work | Sq.ft | 1211.799 | 1066.79 | 1292735.06 | 232692.32 | 1525427.38 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1211.799 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 14th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 15th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1066.79 | 3128419.28 | 563115.48 | 3691534.76 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2932.554 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 16th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2932.554 | 1066.79 | 3128419.28 | 563115.48 | 3691534.76 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2932.554 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | BRICK WORK EXTERNAL | Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1066.79 | 10341882.58 | 1861538.86 | 12203421.44 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | BRICK WORK INTERNAL | Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1066.79 | 10341882.58 | 1861538.86 | 12203421.44 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | INTERNAL PLASTER | Labours for CIVIL-RCC Work | Sq.ft | 9694.394 | 1066.79 | 10341882.58 | 1861538.86 | 12203421.44 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9694.394 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 8th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 9th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 10th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 11th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 12th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 13th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 2nd SLAB PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1066.79 | 3231838.17 | 581730.88 | 3813569.05 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 3rd SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 2944.672 | 3141346.64 | 0 | 0 | 565442.4 | 3706789.04 | 0 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 100
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 4th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 2944.672 | 3141346.64 | 0 | 0 | 565442.4 | 3706789.04 | 0 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 100
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 5th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 6th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 7th SLAB | Labours for CIVIL-RCC Work | Sq.ft | 2944.672 | 1066.79 | 3141346.64 | 565442.4 | 3706789.04 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.672 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 1st SLAB BUILDING | Labours for CIVIL-RCC Work | Sq.ft | 3635.398 | 1066.79 | 3878206.23 | 698077.12 | 4576283.35 | 1.5 | 3635.398 | 3878206.23 | 0 | 0 | 698077.12 | 4576283.35 | 0 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 100
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 1st SLAB PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1066.79 | 3231838.17 | 581730.88 | 3813569.05 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3029.498 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | PLINTH PODIUM | Labours for CIVIL-RCC Work | Sq.ft | 8482.595 | 1066.79 | 9049147.52 | 1628846.56 | 10677994.08 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8482.595 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | 2nd SLAB BUILDING | Labours for CIVIL-RCC Work | Sq.ft | 3029.498 | 1066.79 | 3231838.17 | 581730.88 | 3813569.05 | 1.5 | 3029.498 | 3231838.17 | 0 | 0 | 581730.88 | 3813569.05 | 0 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 100
SPAN TRIDENT | 4 | 0 | 29 Jan 2025 | KASTUREE ASSOCIATES | Misc. Handover | Labours for CIVIL-RCC Work | Sq.ft | 4847.197 | 1066.79 | 5170941.29 | 930769.44 | 6101710.73 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4847.197 | 0 |  |  |  | Nimesh.Makwana | admin | Construction | 29 Jan 2025 |  | RCC | Approved | admin |  | 0
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | 800 MM Dia Piles Boring | RMT | 888 | 1950 | 1731600 | 311688 | 2043288 | 0 | 617.15 | 1203442.5 | 0 | 0 | 216619.66 | 1420062.16 | 270.85 | 623225.84 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  | Excavation | Approved | Nimesh.Makwana |  | 98.8401
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | Chiselling in Rock for Socketing | Hrs | 223.85 | 1000 | 223850 | 40293 | 264143 | 0 | 158.15 | 158150 | 0 | 0 | 28467 | 186617 | 65.7 | 77526 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  | Excavation | Approved | Nimesh.Makwana |  | 100
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | Mud Removing Charges | Trip | 137 | 3200 | 438400 | 78912 | 517312 | 0 | 90 | 288000 | 0 | 0 | 51840 | 339840 | 47 | 177472 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  | Excavation | Approved | Nimesh.Makwana |  | 100
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | RMC Concrete Charges | RMT | 880 | 300 | 264000 | 47520 | 311520 | 0 | 617.15 | 185145 | 0 | 0 | 33326.1 | 218471.1 | 262.85 | 93048.9 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  | Excavation | Approved | Nimesh.Makwana |  | 99.7386
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Fabricating, Lifting & Lowering Steel | MT | 21.03 | 5500 | 115665 | 20819.7 | 136484.7 | 0 | 14.648 | 80564 | 0 | 0 | 14501.52 | 95065.52 | 6.382 | 41419.18 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  |  | Approved | Nimesh.Makwana |  | 99.9905
SPAN TRIDENT | 5 | 0 | 24 Oct 2024 | Harshleen Enterprise LLP | SHORE PILING WORK 800 MM Dia. 24 mtr | Shore Piling Work Mobilization At Site | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 0 | 0 | 9000 | 59000 | 0 | 0 |  |  |  | Nimesh.Makwana | Nimesh.Makwana | Construction | 21 Feb 2025 |  |  | Approved | Nimesh.Makwana |  | 100