## 1Quality Check63730239751917200
| Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register | Quality Check Register
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4 | Total Records: 4 Records 1 To 4
Task_Name | QC_Name | QC_Description | Doc_id | Checked_by | Chk_Date | Status | Remark
First Floor BBM 115MM (CM 1:4)_80210 | Proportion of Mortar | Check for the proportion of mortar as specified. |  | swati.suryawanshi | 43164 | Approved | check
Test 1 RCC COLUMN M20_22849 | Removal of debris | Post excavtion, debris has to be removed properly |  | mandar | 43004 | Approved
02 PCC Demo_104893 | Slump | Check for Slump of the concrete being poured. Is it as per specs? |  | ankush | 43439 | Approved
Test 1 RCC COLUMN M20_22849 | Surface | Cleaning the surface. |  | ankush | 43036 | Approved | tested