## 1Requisition_Tracking-Summary63
| Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary
| From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020 | From Date : 15/08/2020 To date: 15/09/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429 | Total Records: 429 Records 1 to 429
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 144 | 2020-08-17 12:00 | 2020-08-17 12:00 | 4.2216 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 145 | 2020-08-17 12:00 | 2020-08-17 12:00 | 4.2216 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 146 | 2020-08-17 12:00 | 2020-08-17 12:00 | 4.2216 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 147 | 2020-08-17 12:00 | 2020-08-17 12:00 | 4.2216 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 148 | 2020-08-17 12:00 | 2020-08-17 12:00 | 4.2216 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 149 | 2020-08-17 12:00 | 2020-08-17 12:00 | 2.8144 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 150 | 2020-08-17 12:00 | 2020-08-17 12:00 | 2.8144 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 151 | 2020-08-17 12:00 | 2020-08-17 12:00 | 2.8144 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 152 | 2020-08-17 12:00 | 2020-08-17 12:00 | 2.8144 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 153 | 2020-08-17 12:00 | 2020-08-17 12:00 | 2.8144 | 2.8144 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 154 | 2020-08-17 12:00 | 2020-08-17 12:00 | 1.001 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 155 | 2020-08-17 12:00 | 2020-08-17 12:00 | 1.001 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 156 | 2020-08-17 12:00 | 2020-08-17 12:00 | 1.001 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 157 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.6776 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 158 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.3102 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 159 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.6776 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 160 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.3102 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 161 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 162 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 163 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 164 | 2020-08-17 12:00 | 2020-08-17 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | FRP PLAYSTATION 2BUTTERFLY+2FLOWER(BIG KID)- HSN CODE 9506 | Set | 165 | 2020-08-17 12:00 | 2020-08-17 12:00 | 1 | 1 | 0 | Sudhirk | Completed
EELA PHASE-II | FRP PLAYSTATION 2BUTTERFLY+2FLOWER(SMALL KID)- HSN CODE 9506 | Set | 166 | 2020-08-17 12:00 | 2020-08-17 12:00 | 1 | 1 | 0 | Sudhirk | Completed
EELA PHASE-II | RUBBER HAND GLOVES (USE AND THROUGH) - HSN CODE 4015 | Pair | 167 | 2020-08-17 12:00 | 2020-08-18 12:00 | 200 | 200 | 0 | Madan | Completed
EELA PHASE-II | WHITE PLATE 4 MODULE- HSN CODE 85381090 | Nos | 168 | 2020-08-18 | 2020-08-25 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | WHITE PLATE 12 MODULE- HSN CODE 85381090 | Nos | 169 | 2020-08-18 | 2020-08-25 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | WHITE PLATE 2 MODULE- HSN CODE 85381090 | Nos | 170 | 2020-08-18 | 2020-08-25 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | 6 AMP BELL PUSH WITH INDICATOR -2 MODULE- HSN CODE 85365020 | Nos | 171 | 2020-08-18 | 2020-08-25 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | DOOR BELL- HSN CODE 8531 | Nos | 172 | 2020-08-18 | 2020-08-25 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | BLANKING PLATE - 1MODULE- HSN CODE 85381090 | Nos | 173 | 2020-08-18 | 2020-08-25 | 22 | 22 | 0 | Rajendra | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 174 | 2020-08-18 12:00 | 2020-08-18 12:00 | 3.9432 | 3.9432 | 0 | Sudhirk | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 175 | 2020-08-18 12:00 | 2020-08-18 12:00 | 4.2216 | 4.2216 | 0 | Sudhirk | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 176 | 2020-08-18 12:00 | 2020-08-18 12:00 | 4.2216 | 4.2216 | 0 | Sudhirk | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 177 | 2020-08-18 12:00 | 2020-08-18 12:00 | 4.2216 | 4.2216 | 0 | Sudhirk | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 178 | 2020-08-18 12:00 | 2020-08-18 12:00 | 4.2216 | 4.2216 | 0 | Sudhirk | Completed
EELA PHASE-II | ANIMAL MERRY GO ROUND- HSN CODE 9506 | Set | 179 | 2020-08-18 | 2020-07-09 | 1 | 1 | 0 | Kiran | Completed
EELA PHASE-II | BALANCING BEAMS (SET OF 3) - HSN CODE 9506 | Set | 180 | 2020-08-18 | 2020-07-09 | 1 | 1 | 0 | Kiran | Completed
EELA PHASE-II | LOOP SCRAMBLER- HSN CODE 9506 | Set | 181 | 2020-08-18 | 2020-07-09 | 1 | 1 | 0 | Kiran | Completed
EELA PHASE-II | NET ROCK CLIMBER (1.5M HEIGHT)- HSN CODE 9506 | Set | 182 | 2020-08-18 | 2020-07-09 | 1 | 1 | 0 | Kiran | Completed
EELA PHASE-II | STANDARD SEA SAW- - HSN CODE 9506 | Set | 183 | 2020-08-18 | 2020-07-09 | 1 | 1 | 0 | Kiran | Completed
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 198 | 2020-08-19 12:00 | 2020-08-19 12:00 | 10 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 199 | 2020-08-19 12:00 | 2020-08-19 12:00 | 12 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 200 | 2020-08-19 12:00 | 2020-08-19 12:00 | 9 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 201 | 2020-08-19 12:00 | 2020-08-19 12:00 | 12 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 202 | 2020-08-19 12:00 | 2020-08-19 12:00 | 12 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 203 | 2020-08-19 12:00 | 2020-08-19 12:00 | 12 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | CONCEALED BODY DIVERTER- HSN CODE 84818020 | Nos | 204 | 2020-08-19 12:00 | 2020-08-19 12:00 | 12 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 205 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.6288 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 206 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.8144 | 2.8144 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 207 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.8144 | 2.8144 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 208 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.8144 | 2.8144 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 209 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.8144 | 2.8144 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 210 | 2020-08-19 12:00 | 2020-08-19 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 211 | 2020-08-19 12:00 | 2020-08-19 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 212 | 2020-08-19 12:00 | 2020-08-19 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 213 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 214 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 215 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 216 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 217 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 218 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 219 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.8206 | 0.8206 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 220 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 221 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 222 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 223 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 224 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 225 | 2020-08-19 12:00 | 2020-08-19 12:00 | 2.8673 | 2.8673 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 226 | 2020-08-19 12:00 | 2020-08-19 12:00 | 0.5072 | 0.5072 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 227 | 2020-08-20 12:00 | 2020-08-20 12:00 | 2.6288 | 2.6288 | 0 | Rohan | Completed
EELA PHASE-II | RUBBER HAND GLOVES (USE AND THROUGH) - HSN CODE 4015 | Pair | 228 | 2020-08-20 | 2020-08-27 | 250 | 250 | 0 | Rajendra | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 230 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 231 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 232 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 233 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 234 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 235 | 2020-08-21 12:00 | 2020-08-21 12:00 | 25 | 25 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 236 | 2020-08-21 12:00 | 2020-08-21 12:00 | 37.492 | 37.492 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 237 | 2020-08-21 12:00 | 2020-08-21 12:00 | 37.492 | 37.492 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 238 | 2020-08-21 12:00 | 2020-08-21 12:00 | 37.492 | 37.492 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 239 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6.5424 | 6.5424 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 240 | 2020-08-21 12:00 | 2020-08-21 12:00 | 32.565 | 32.565 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 241 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 242 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 243 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 244 | 2020-08-21 12:00 | 2020-08-21 12:00 | 31.005 | 31.005 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 245 | 2020-08-21 12:00 | 2020-08-21 12:00 | 31.005 | 31.005 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 246 | 2020-08-21 12:00 | 2020-08-21 12:00 | 31.005 | 31.005 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 247 | 2020-08-21 12:00 | 2020-08-21 12:00 | 31.005 | 31.005 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 248 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 249 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 250 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 251 | 2020-08-21 12:00 | 2020-08-21 12:00 | 20 | 20 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 252 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 253 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 254 | 2020-08-21 12:00 | 2020-08-21 12:00 | 30 | 30 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 255 | 2020-08-21 12:00 | 2020-08-21 12:00 | 79.155 | 79.155 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 256 | 2020-08-21 12:00 | 2020-08-21 12:00 | 79.155 | 79.155 | 0 | Rohan | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 257 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 258 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 259 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 260 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 261 | 2020-08-21 12:00 | 2020-08-21 12:00 | 31.005 | 31.005 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 262 | 2020-08-21 12:00 | 2020-08-21 12:00 | 21 | 21 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 263 | 2020-08-21 12:00 | 2020-08-21 12:00 | 21 | 21 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 264 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 265 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 266 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 267 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 268 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 269 | 2020-08-21 12:00 | 2020-08-21 12:00 | 15 | 15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 270 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 271 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1 | 1 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 272 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 273 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.15 | 1.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 274 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.5 | 2.5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 275 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1 | 1 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 276 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1 | 1 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 277 | 2020-08-21 12:00 | 2020-08-21 12:00 | 0.75 | 0.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 278 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.42 | 1.42 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 279 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1 | 1 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 280 | 2020-08-21 12:00 | 2020-08-21 12:00 | 0.75 | 0.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 281 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.5 | 1.5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 282 | 2020-08-21 12:00 | 2020-08-21 12:00 | 7.11 | 7.11 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 283 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.0625 | 2.0625 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 284 | 2020-08-21 12:00 | 2020-08-21 12:00 | 3.15 | 3.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 285 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.75 | 1.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 286 | 2020-08-21 12:00 | 2020-08-21 12:00 | 30 | 30 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 287 | 2020-08-21 12:00 | 2020-08-21 12:00 | 3.15 | 3.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 288 | 2020-08-21 12:00 | 2020-08-21 12:00 | 7.11 | 7.11 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 289 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.0625 | 2.0625 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 290 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.75 | 1.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 291 | 2020-08-21 12:00 | 2020-08-21 12:00 | 30 | 30 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 292 | 2020-08-21 12:00 | 2020-08-21 12:00 | 3.15 | 3.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 293 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.75 | 1.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 294 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.0625 | 2.0625 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 295 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 296 | 2020-08-21 12:00 | 2020-08-21 12:00 | 30 | 30 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 297 | 2020-08-21 12:00 | 2020-08-21 12:00 | 7.11 | 7.11 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 298 | 2020-08-21 12:00 | 2020-08-21 12:00 | 3.15 | 3.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 299 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.0625 | 2.0625 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 300 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.75 | 1.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 301 | 2020-08-21 12:00 | 2020-08-21 12:00 | 30 | 30 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 302 | 2020-08-21 12:00 | 2020-08-21 12:00 | 7.11 | 7.11 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 303 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2.0625 | 2.0625 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 304 | 2020-08-21 12:00 | 2020-08-21 12:00 | 1.75 | 1.75 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 305 | 2020-08-21 12:00 | 2020-08-21 12:00 | 3.15 | 3.15 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 306 | 2020-08-21 12:00 | 2020-08-21 12:00 | 5 | 5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 307 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 308 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 309 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 310 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 311 | 2020-08-21 12:00 | 2020-08-21 12:00 | 8 | 8 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 312 | 2020-08-21 12:00 | 2020-08-21 12:00 | 8 | 8 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 313 | 2020-08-21 12:00 | 2020-08-21 12:00 | 5 | 5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 314 | 2020-08-21 12:00 | 2020-08-21 12:00 | 5 | 5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 315 | 2020-08-21 12:00 | 2020-08-21 12:00 | 5 | 5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 316 | 2020-08-21 12:00 | 2020-08-21 12:00 | 4 | 4 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 317 | 2020-08-21 12:00 | 2020-08-21 12:00 | 5 | 5 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 318 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 319 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 320 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 321 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 322 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 323 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 324 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 325 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 326 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 327 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 328 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 329 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 330 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 331 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 332 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 333 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 334 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6 | 6 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 335 | 2020-08-21 12:00 | 2020-08-21 12:00 | 2 | 2 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 336 | 2020-08-21 12:00 | 2020-08-21 12:00 | 10 | 10 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 337 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6.5424 | 6.5424 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 338 | 2020-08-21 12:00 | 2020-08-21 12:00 | 17.3072 | 17.3072 | 0 | Kalpesh | Completed
EELA PHASE-II | CEMENT 43 GRADE OPC- HSN CODE 25232910 | Bag | 339 | 2020-08-21 12:00 | 2020-08-21 12:00 | 6.5424 | 6.5424 | 0 | Kalpesh | Completed
EELA PHASE-II | RUBBER HAND GLOVES (USE AND THROUGH) - HSN CODE 4015 | Pair | 340 | 2020-08-21 | 2020-07-09 | 300 | 300 | 0 | Vishwanath | Completed
EELA PHASE-II | SAFETY JACKET ORANGE - HSN CODE 6203 | Nos | 341 | 2020-08-21 | 2020-07-09 | 20 | 20 | 0 | Vishwanath | Completed
EELA PHASE-II | SAFETY SHOES- HSN CODE 6403 | Pair | 342 | 2020-08-21 | 2020-07-09 | 12 | 12 | 0 | Vishwanath | Completed
EELA PHASE-II | READY MIX PLASTER - HSN CODE 3824 | MT | 343 | 2020-08-21 | 2020-08-25 | 25 | 25 | 0 | Nikhil | Completed | Club House Ext.Plaster
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 348 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.688 | 1.688 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 349 | 2020-08-24 12:00 | 2020-08-24 12:00 | 2.533 | 2.533 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 350 | 2020-08-24 12:00 | 2020-08-24 12:00 | 3.2004 | 3.2004 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 351 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.3 | 0.3 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 352 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.138 | 0.138 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 353 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2275 | 0.2275 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 354 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.1008 | 0.1008 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 355 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2275 | 0.2275 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 356 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.1008 | 0.1008 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 357 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.688 | 1.688 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 358 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.1008 | 0.1008 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 359 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2275 | 0.2275 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 360 | 2020-08-24 12:00 | 2020-08-24 12:00 | 2.55 | 2.55 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 361 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 362 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 363 | 2020-08-24 12:00 | 2020-08-24 12:00 | 3.22 | 3.22 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 364 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 365 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 366 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.22 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 367 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.72 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 368 | 2020-08-24 12:00 | 2020-08-24 12:00 | 2.1336 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 369 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 370 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.092 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 371 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2528 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 372 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.112 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 373 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2528 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 374 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.112 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 375 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.72 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 376 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.112 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 377 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2528 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 378 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1.72 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 379 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.112 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 380 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2528 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 381 | 2020-08-24 12:00 | 2020-08-24 12:00 | 2.1 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 382 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.2528 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | RIVER SAND CHAAL : HSN CODE 2505 | Brass | 383 | 2020-08-24 12:00 | 2020-08-24 12:00 | 0.112 | 0 | 0 | Kalpesh | Deleted
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 384 | 2020-08-24 12:00 | 2020-08-24 12:00 | 388 | 388 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 385 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1550.25 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 386 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1151.25 | 1151.25 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 387 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1550.25 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 388 | 2020-08-24 12:00 | 2020-08-24 12:00 | 789 | 789 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 389 | 2020-08-24 12:00 | 2020-08-24 12:00 | 233 | 233 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 390 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1550.25 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 391 | 2020-08-24 12:00 | 2020-08-24 12:00 | 388 | 388 | 0 | Kalpesh | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 419 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1550.25 | 0 | Rohan | Completed
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 420 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 421 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 0 | 0 | Rohan | Deleted
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 422 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1300 | 0 | Rohan | Approved
EELA PHASE-II | BLOCK FIXING MORTER- HSN CODE 38245090 | Kg | 423 | 2020-08-24 12:00 | 2020-08-24 12:00 | 1550.25 | 1550 | 0 | Rohan | Approved
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 426 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 427 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 428 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 429 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 430 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 431 | 2020-08-25 12:00 | 2020-08-25 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | CP BOTTLE TRAP EXTENSION PIPE- HSN CODE 7418 | Nos | 432 | 2020-08-25 12:00 | 2020-08-25 12:00 | 8 | 8 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 120 X 12 - HSN CODE 7318 | Nos | 433 | 2020-08-25 12:00 | 2020-08-28 12:00 | 4 | 4 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 120 X 12 - HSN CODE 7318 | Nos | 434 | 2020-08-25 12:00 | 2020-08-28 12:00 | 4 | 4 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 120 X 12 - HSN CODE 7318 | Nos | 435 | 2020-08-25 12:00 | 2020-08-28 12:00 | 4 | 4 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 120 X 12 - HSN CODE 7318 | Nos | 436 | 2020-08-25 12:00 | 2020-08-28 12:00 | 4 | 4 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 120 X 12 - HSN CODE 7318 | Nos | 437 | 2020-08-25 12:00 | 2020-08-28 12:00 | 4 | 4 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 438 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 439 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 440 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 441 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 442 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 443 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 444 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 445 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 446 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 447 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 448 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 449 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 450 | 2020-08-25 12:00 | 2020-08-28 12:00 | 6 | 6 | 0 | Vaibhav | Completed
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 451 | 2020-08-25 12:00 | 2020-08-28 12:00 | 2 | 2 | 0 | Vaibhav | Completed
EELA PHASE-II | AWNING TENSILE FABRIC & SUN BLINDS - HSN CODE 6306 | Sqft | 452 | 2020-08-25 | 2020-07-09 | 2000 | 2000 | 0 | Sudhirk | Completed
EELA PHASE-II | MS SQUARE BAR 12MM- HSN CODE 7215 | MT | 453 | 2020-08-27 12:00 | 2020-08-29 12:00 | 0.132 | 0.132 | 0 | Vaibhav | Completed
EELA PHASE-II | MS SQUARE BAR 12MM- HSN CODE 7215 | MT | 454 | 2020-08-27 12:00 | 2020-08-29 12:00 | 0.132 | 0.132 | 0 | Vaibhav | Completed
EELA PHASE-II | MS SQUARE BAR 12MM- HSN CODE 7215 | MT | 455 | 2020-08-27 12:00 | 2020-08-29 12:00 | 0.04 | 0.04 | 0 | Vaibhav | Completed
EELA PHASE-II | READY MIX PLASTER - HSN CODE 3824 | MT | 457 | 2020-08-27 | 2020-07-09 | 25 | 25 | 0 | Nikhil | Completed | for club house external plaster
EELA PHASE-II | USB COMBO SET (KEY BOARD & MOUSE)- HSN CODE 8471 | Set | 458 | 2020-08-28 12:00 | 2020-09-01 12:00 | 6 | 6 | 0 | Madan | Completed | For Maintenance work
EELA PHASE-II | FASTENER 60 X 8- HSN CODE 7318 | Nos | 478 | 2020-08-31 | 2020-09-07 | 20 | 20 | 0 | Vaibhav | Completed
EELA PHASE-II | FLY ASH BRICKS 9"L X 4"W X 3"H- HSN CODE 6815 | Nos | 511 | 2020-08-31 | 2020-08-31 | 4631.8965 | 4631.8965 | 0 | nikhil | Completed | For Phase 2 Gas Bank BBM work
EELA PHASE-II | FLY ASH BRICKS 9"L X 4"W X 3"H- HSN CODE 6815 | Nos | 512 | 2020-08-31 | 2020-07-31 | 1993.6645 | 1993.6645 | 0 | nikhil | Completed | For Phase 2 Gas Bank BBM work
EELA PHASE-II | DIESEL- HSN CODE 997212 | Ltr | 515 | 2020-08-31 | 2020-09-01 | 600 | 600 | 0 | sharnappa | Completed | 125 Kv DG, JCB & Tractors
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 516 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 517 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 518 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.63 | 0.63 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 519 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 520 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 521 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 63MM (2.5")- HSN CODE 7318 | Kg | 522 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.819 | 0.819 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 523 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 524 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 525 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.472 | 0.472 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 526 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 527 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 528 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | GI NUT BOLTS WITH WASHER 8MM X 40MM (1.5")- HSN CODE 7318 | Kg | 529 | 2020-09-02 12:00 | 2020-09-02 12:00 | 0.614 | 0.614 | 0 | Vaibhav | Completed
EELA PHASE-II | COPPER FLEXIBLE CABLE 1.5 SQMM X 7 CORE- HSN CODE 8544 | Rmt | 530 | 2020-09-02 | 2020-07-09 | 70 | 70 | 0 | Nikhil | Completed | for panel to pump wire sump well podium
EELA PHASE-II | COPPER FLEXIBLE CABLE 6 SQMM X 4 CORE- HSN CODE 8544 | Rmt | 531 | 2020-09-02 | 2020-07-09 | 220 | 220 | 0 | Nikhil | Completed | for main supply to pump panel
EELA PHASE-II | FRP LOUVER - 1330 X 75 X 25MM- HSN CODE -70199090 | Nos | 532 | 2020-09-02 12:00 | 2020-09-02 12:00 | 210 | 210 | 0 | Rohan | Completed
EELA PHASE-II | FRP LOUVER - 2030 X 75 X 25MM- HSN CODE -70199090 | Nos | 533 | 2020-09-02 12:00 | 2020-09-02 12:00 | 280 | 280 | 0 | Rohan | Completed
EELA PHASE-II | INSULATION TAPE- HSN CODE 8546 | Nos | 534 | 2020-09-02 | 2020-07-09 | 100 | 100 | 0 | Nikhil | Completed | for light connection work
EELA PHASE-II | CAT 6 ARMOURED CABLE- HSN CODE 8544 | Rmt | 535 | 2020-09-02 | 2020-09-07 | 310 | 310 | 0 | Nikhil | Completed | For E F Building CCTV Connection
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 536 | 2020-09-02 12:00 | 2020-09-02 12:00 | 8 | 8 | 0 | Kalpesh | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 537 | 2020-09-02 12:00 | 2020-09-02 12:00 | 8 | 8 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 538 | 2020-09-02 12:00 | 2020-09-02 12:00 | 12 | 12 | 0 | Vaibhav | Completed
EELA PHASE-II | LATERAL PIPE 16MM TUBE (INLINE)- HSN CODE 8424 | Mtr | 539 | 2020-09-03 | 2020-09-07 | 1000 | 1000 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | IMPACT SPRINKLER POPUP 805- HSN CODE 8424 | Nos | 540 | 2020-09-03 | 2020-07-09 | 28 | 28 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING 16MM ELBOW- HSN CODE 8424 | Nos | 541 | 2020-09-03 | 2020-07-09 | 200 | 200 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING 16MM END CAP- HSN CODE 8424 | Nos | 542 | 2020-09-03 | 2020-07-09 | 200 | 200 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING 16MM GROMMET- HSN CODE 8424 | Nos | 543 | 2020-09-03 | 2020-09-07 | 200 | 200 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING 16MM JOINER- HSN CODE 8424 | Nos | 544 | 2020-09-03 | 2020-07-09 | 300 | 300 | 0 | Nikhil | Completed | for podium Garden
EELA PHASE-II | POLY FITTING 16MM TAKE OFF- HSN CODE 8424 | Nos | 545 | 2020-09-03 | 2020-09-07 | 200 | 200 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING 16MM TEE- HSN CODE 8424 | Nos | 546 | 2020-09-03 | 2020-09-07 | 200 | 200 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | CPVC SOLVENT CEMENT 946 ML- HSN CODE 3506 | Nos | 547 | 2020-09-03 | 2020-09-07 | 3 | 3 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING DRIPPER (8LPH) - HSN CODE 8424 | Nos | 548 | 2020-09-03 | 2020-09-07 | 200 | 0 | 0 | Nikhil | Deleted | for podium garden
EELA PHASE-II | PVC ELBOW 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 549 | 2020-09-03 | 2020-09-07 | 60 | 0 | 0 | Nikhil | Deleted | for podium garden
EELA PHASE-II | PVC ELBOW 50MM (1.5") (SELFIT)- HSN CODE 3917 | Nos | 550 | 2020-09-03 | 2020-07-09 | 20 | 20 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | POLY FITTING DRIPPER (8LPH) - HSN CODE 8424 | Nos | 551 | 2020-09-03 | 2020-07-09 | 200 | 200 | 0 | Nikhil | Completed
EELA PHASE-II | PVC ELBOW 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 552 | 2020-09-03 | 2020-07-09 | 60 | 60 | 0 | Nikhil | Completed
EELA PHASE-II | PVC ENDCAP 40MM (1.25") PLAIN (SELFIT)- HSN CODE 3917 | Nos | 553 | 2020-09-03 | 2020-09-07 | 20 | 20 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC ENDCAP 50MM (1.5") THREADED (SELFIT)- HSN CODE 3917 | Nos | 554 | 2020-09-03 | 2020-09-07 | 5 | 0 | 0 | Nikhil | Deleted | for podium garden
EELA PHASE-II | PVC ENDCAP 50MM (1.5") THREADED (SELFIT)- HSN CODE 3917 | Nos | 555 | 2020-09-03 | 2020-07-09 | 5 | 5 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC FTA 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 556 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC FTA 50MM (1.5") (SELFIT)- HSN CODE 3917 | Nos | 557 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC MTA 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 558 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC MTA 50MM (1.5") (SELFIT)- HSN CODE 3917 | Nos | 559 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC PIPE 40MM 1.25" X 6KG (SELFIT)- HSN CODE 3917 | Mtr | 560 | 2020-09-03 | 2020-09-07 | 400 | 0 | 0 | Nikhil | Deleted | for podium garden
EELA PHASE-II | PVC PIPE 40MM 1.25" X 6KG (SELFIT)- HSN CODE 3917 | Mtr | 561 | 2020-09-03 | 2020-07-09 | 400 | 400 | 0 | Nikhil | Completed
EELA PHASE-II | PVC PIPE 50MM 1.5" X 6KG (SELFIT)- HSN CODE 3917 | Mtr | 562 | 2020-09-03 | 2020-09-07 | 100 | 100 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC REDUCER SOCKET 50MM 1.5"X40MM 1.25" SELFIT-HSN CODE 3917 | Nos | 563 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC SERVICE SADDLE 40MM X 20MM (SELFIT) - HSN CODE 39174000 | Nos | 564 | 2020-09-03 | 2020-09-07 | 15 | 15 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC SERVICE SADDLE 50MM X 15MM (SELFIT) -HSN CODE 39174000 | Nos | 565 | 2020-09-03 | 2020-09-07 | 30 | 30 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC SOCKET 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 566 | 2020-09-03 | 2020-09-07 | 30 | 30 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC SOCKET 50MM (1.5") (SELFIT)- HSN CODE 3917 | Nos | 567 | 2020-09-03 | 2020-09-07 | 20 | 20 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC TEE 40MM (1.25") (SELFIT)- HSN CODE 3917 | Nos | 568 | 2020-09-03 | 2020-09-07 | 40 | 40 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC TEE 50MM (1.5") (SELFIT)- HSN CODE 3917 | Nos | 569 | 2020-09-03 | 2020-09-07 | 10 | 10 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | PVC VALVE BOX 6"- HSN CODE 8424 | Nos | 570 | 2020-09-03 | 2020-09-07 | 13 | 13 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | SWING JOINT 1/2"- HSN CODE 8424 | Nos | 571 | 2020-09-03 | 2020-07-09 | 28 | 28 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | TEFLON TAPE- HSN CODE 3920 | Nos | 572 | 2020-09-03 | 2020-09-07 | 36 | 36 | 0 | Nikhil | Completed | for podium garden
EELA PHASE-II | SANITIZER LIQUID HSN CODE : 3004 | Ltr | 573 | 2020-09-04 | 2020-09-11 | 10 | 10 | 0 | Rajendra | Completed
EELA PHASE-II | SANITIZER LIQUID HSN CODE : 3004 | Ltr | 574 | 2020-09-04 | 2020-09-11 | 10 | 10 | 0 | Rajendra | Completed
EELA PHASE-II | SURFACE MOUNTED 12W LED FITTING-ID-2767- HSN CODE 94054090 | Nos | 576 | 2020-08-21 | 2020-08-21 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 577 | 2020-09-05 | 2020-09-07 | 0.65 | 0.65 | 0 | Nikhil | Completed | for internal plaster
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 578 | 2020-09-05 | 2020-09-07 | 1.32 | 1.32 | 0 | Nikhil | Completed | for internal plaster
EELA PHASE-II | FLY ASH BRICKS 9"L X 4"W X 3"H- HSN CODE 6815 | Nos | 579 | 2020-09-06 | 2020-09-09 | 10000 | 10000 | 0 | Nikhil | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 580 | 2020-09-07 12:00 | 2020-09-07 12:00 | 5 | 5 | 0 | nikhil | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 581 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 582 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.8206 | 0.8206 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 583 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 584 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 585 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 586 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 587 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 588 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 589 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 590 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 591 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 592 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 593 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 594 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 595 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 596 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.8206 | 0.8206 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 597 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 598 | 2020-09-07 12:00 | 2020-09-07 12:00 | 1.001 | 1.001 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 599 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.6776 | 0.6776 | 0 | Rohan | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 600 | 2020-09-07 12:00 | 2020-09-07 12:00 | 0.3102 | 0.3102 | 0 | Rohan | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 601 | 2020-09-07 12:00 | 2020-09-07 12:00 | 4 | 4 | 0 | Rohan | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 602 | 2020-09-07 12:00 | 2020-09-07 12:00 | 3 | 3 | 0 | Rohan | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 603 | 2020-09-07 12:00 | 2020-09-07 12:00 | 3 | 3 | 0 | Rohan | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 604 | 2020-09-07 12:00 | 2020-09-07 12:00 | 3 | 3 | 0 | Rohan | Completed
EELA PHASE-II | GYPSUM ELITE 100- HSN CODE 25202010 | MT | 605 | 2020-09-07 12:00 | 2020-09-07 12:00 | 3 | 3 | 0 | Rohan | Completed
EELA PHASE-II | BARICATION TAPE- HSN CODE -3926 | Rmt | 606 | 2020-09-07 | 2020-07-09 | 500 | 500 | 0 | Vishwanath | Completed
EELA PHASE-II | GUM BOOT- HSN CODE 6402 | Pair | 607 | 2020-09-07 | 2020-07-09 | 7 | 7 | 0 | Vishwanath | Completed
EELA PHASE-II | RUBBER HAND GLOVES FOR ACID WASH- HSN CODE 4015 | Nos | 608 | 2020-09-07 | 2020-07-09 | 15 | 15 | 0 | Vishwanath | Completed
EELA PHASE-II | RMC M-25- HSN CODE 38245010 | Cum | 632 | 2020-09-09 | 2020-09-10 | 100 | 0 | 0 | Nikhil | Deleted | for road trimix
EELA PHASE-II | DIESEL- HSN CODE 997212 | Ltr | 668 | 2020-09-12 12:00 | 2020-09-12 12:00 | 600 | 600 | 0 | sharnappa | Completed
EELA PHASE-II | FRP JALI BOX TYPE - 7.8MTR X 1.5MTR- HSN CODE -70199090 | Nos | 674 | 2020-09-14 | 2020-07-09 | 7 | 7 | 0 | Sudhirk | Completed
EELA PHASE-II | THERMOMETER (FOR BODY TEMPERATURE) - HSN CODE 9025 | Nos | 675 | 2020-09-12 | 2020-09-12 | 1 | 1 | 0 | Rajendra | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 676 | 2020-09-14 12:00 | 2020-09-14 12:00 | 1.1 | 1.1 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 677 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 678 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 679 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 680 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 681 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 682 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 683 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 684 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 685 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 686 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 687 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 688 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 689 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 690 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 691 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 692 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 693 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.3792 | 0.3792 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 694 | 2020-09-14 12:00 | 2020-09-14 12:00 | 0.168 | 0.168 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 695 | 2020-09-14 12:00 | 2020-09-14 12:00 | 4.2216 | 4.2216 | 0 | Kalpesh | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 696 | 2020-09-14 | 2020-07-10 | 8.4686 | 8.4686 | 0 | nikhil | Completed
EELA PHASE-II | CRUSH SAND- HSN CODE 2517 | Brass | 697 | 2020-09-14 | 2020-07-09 | 3.589 | 3.589 | 0 | nikhil | Completed
EELA PHASE-II | RMC M-15- HSN CODE 38245010 | Cum | 698 | 2020-09-14 | 2020-09-16 | 100 | 100 | 0 | nikhil | Completed
EELA PHASE-II | RUBBLE- HSN CODE 2517 | Brass | 699 | 2020-09-14 | 2020-07-09 | 118.5408 | 0 | 0 | nikhil | Unapproved
EELA PHASE-II | BEARING- HSN CODE 85030010 | Nos | 700 | 2020-09-14 | 2020-09-15 | 1 | 1 | 0 | Vishwanath | Completed
EELA PHASE-II | MICRO CONTROLER- HSN CODE 85364100 | Nos | 701 | 2020-09-14 | 2020-09-15 | 1 | 1 | 0 | Vishwanath | Completed
EELA PHASE-II | POWER SUPPLY- HSN CODE 9032 | Nos | 702 | 2020-09-14 | 2020-09-15 | 1 | 1 | 0 | Vishwanath | Completed
EELA PHASE-II | PRESSURE TRANSMITTER FOR PUMP- HSN CODE 9032 | Nos | 703 | 2020-09-14 | 2020-09-15 | 1 | 1 | 0 | Vishwanath | Completed
EELA PHASE-II | PUMP REWINDING - HSN CODE 85030010 | Nos | 704 | 2020-09-14 | 2020-09-15 | 1 | 1 | 0 | Vishwanath | Completed
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 705 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.8215 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 706 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 707 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 708 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 709 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 710 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.0912 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 711 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 712 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.6776 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 713 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 714 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.6776 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 715 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 716 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.6776 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 717 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 718 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.6776 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 719 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 720 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.6776 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 721 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.3102 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 722 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Rohan | Unapproved
EELA PHASE-II | RUBBER HAND GLOVES (USE AND THROUGH) - HSN CODE 4015 | Pair | 723 | 2020-09-15 | 2020-09-22 | 500 | 500 | 0 | Rajendra | Completed
EELA PHASE-II | FRP JALI BOX TYPE - 7.8MTR X 1.5MTR- HSN CODE -70199090 | Nos | 724 | 2020-09-15 | 2020-07-10 | 27 | 0 | 0 | Nikhil | Unapproved | For Podium Elevation
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 725 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.8215 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 726 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 727 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 728 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 729 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 730 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.8 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 731 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.8 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 732 | 2020-09-15 12:00 | 2020-09-15 12:00 | 0.8 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 733 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 734 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 735 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 736 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.001 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | RIVER SAND- HSN CODE 2505 | Brass | 737 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1.0912 | 0 | 0 | Kalpesh | Unapproved
EELA PHASE-II | LIGHTNING ARRESTOR- HSN CODE 8535 | Set | 738 | 2020-09-15 12:00 | 2020-09-15 12:00 | 1 | 0 | 0 | Rohan | Unapproved