## 1Requisition_Tracking-Summary63
| Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary
| From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020 | From Date : 03/10/2020 To date: 03/11/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163 | Total Records: 163 Records 1 to 163
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
S9 | BASALT STONE (RIVER WASH) - HSN CODE 2516 | Sqft | 648 | 2020-10-03 12:00 | 2020-10-05 12:00 | 86.25 | 86.25 | 0 | Indrajeet | Completed | For toilet and pantry flooring.
S9 | BASALT STONE (RIVER WASH) - HSN CODE 2516 | Sqft | 648 | 2020-10-03 12:00 | 2020-10-05 12:00 | 86.25 | 86.25 | 0 | Indrajeet | Completed | For toilet and pantry flooring.
S9 | BASALT STONE (RIVER WASH) - HSN CODE 2516 | Sqft | 648 | 2020-10-03 12:00 | 2020-10-05 12:00 | 86.25 | 86.25 | 0 | Indrajeet | Completed | For toilet and pantry flooring.
S9 | BASALT STONE (RIVER WASH) - HSN CODE 2516 | Sqft | 648 | 2020-10-03 12:00 | 2020-10-05 12:00 | 86.25 | 86.25 | 0 | Indrajeet | Completed | For toilet and pantry flooring.
S9 | BRONYA AQUABLOCK NF- WP COATING CHEMICAL - HSN CODE 3824 | Ltr | 649 | 2020-10-03 | 2020-10-06 | 51 | 51 | 0 | Indrajeet | Completed
S9 | BRONYA AQUABLOCK NF- WP COATING CHEMICAL - HSN CODE 3824 | Ltr | 649 | 2020-10-03 | 2020-10-06 | 27 | 27 | 0 | Indrajeet | Completed
S9 | BRONYA AQUABLOCK NF- WP COATING CHEMICAL - HSN CODE 3824 | Ltr | 649 | 2020-10-03 | 2020-10-06 | 22 | 22 | 0 | Indrajeet | Completed
S9 | ALASKA WHITE GRANITE- HSN CODE 6802 | Sqft | 650 | 2020-10-05 12:00 | 2020-10-07 12:00 | 10 | 10 | 0 | Indrajeet | Completed | For lift cladding.
S9 | ALASKA WHITE GRANITE- HSN CODE 6802 | Sqft | 650 | 2020-10-05 12:00 | 2020-10-07 12:00 | 180 | 180 | 0 | Indrajeet | Completed | For lift cladding.
S9 | ALASKA WHITE GRANITE- HSN CODE 6802 | Sqft | 650 | 2020-10-05 12:00 | 2020-10-07 12:00 | 180 | 180 | 0 | Indrajeet | Completed | For lift cladding.
S9 | ALASKA WHITE GRANITE- HSN CODE 6802 | Sqft | 650 | 2020-10-05 12:00 | 2020-10-07 12:00 | 180 | 180 | 0 | Indrajeet | Completed | For lift cladding.
S9 | UPVC BALL VALVE 1¼"(32MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 1¼"(32MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 3 | 3 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 1½"(40MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 5 | 5 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 2"(50MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC PIPE ( 3MTR ) 1¼" ( 32MM )- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC PIPE(3MTR) 1½"(40MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC SOCKET/COUPLING 1¼"(32MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC SOCKET/COUPLING 1½"(40MM)- HSN CODE 3917 | Nos | 651 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER BUSHING 1¼"(32MM) X ½"(15MM)- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER BUSHING 1¼"(32MM) X ½"(15MM)- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER BUSHING 1¼"(32MM) X ½"(15MM)- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER BUSHING 1¼"(32MM) X ½"(15MM)- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER BUSHING 1¼"(32MM) X ½"(15MM)- HSN CODE 3917 | Nos | 652 | 2020-10-05 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC BRASS ELBOW 15MM(½")- HSN CODE 3917 | Nos | 653 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC BRASS ELBOW 15MM(½")- HSN CODE 3917 | Nos | 653 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC BRASS ELBOW 15MM(½")- HSN CODE 3917 | Nos | 653 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC BRASS ELBOW 15MM(½")- HSN CODE 3917 | Nos | 653 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC BRASS ELBOW 15MM(½")- HSN CODE 3917 | Nos | 653 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC SOCKET 15MM(½")- HSN CODE 3917 | Nos | 654 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC SOCKET 15MM(½")- HSN CODE 3917 | Nos | 654 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC SOCKET 15MM(½")- HSN CODE 3917 | Nos | 654 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC SOCKET 15MM(½")- HSN CODE 3917 | Nos | 654 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC SOCKET 15MM(½")- HSN CODE 3917 | Nos | 654 | 2020-10-05 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CURING PIPE ¾"- HSN CODE 3917 | Nos | 655 | 2020-10-06 12:00 | 2020-10-08 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | FEVIKWICK - HSN CODE 35061000 | Nos | 656 | 2020-10-07 12:00 | 2020-10-08 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC FEMALE ADAPTER (FAPT) ¾"(20MM)- HSN CODE 3917 | Nos | 657 | 2020-10-07 12:00 | 2020-10-10 12:00 | 107 | 107 | 0 | Indrajeet | Completed
S9 | UPVC SOCKET/COUPLING ¾"(20MM)- HSN CODE 3917 | Nos | 658 | 2020-10-07 12:00 | 2020-10-10 12:00 | 160 | 160 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | UPVC TEE ¾"(20MM)- HSN CODE 3917 | Nos | 658 | 2020-10-07 12:00 | 2020-10-10 12:00 | 262 | 262 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | UPVC ELBOW ¾"(20MM)- HSN CODE 3917 | Nos | 658 | 2020-10-07 12:00 | 2020-10-10 12:00 | 524 | 524 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | GI WALL Z BRACKET 32X50X32X4' LONG(2MM THK)- HSN CODE 7216 | Nos | 659 | 2020-10-07 12:00 | 2020-10-10 12:00 | 40 | 40 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | GI U CLAMP ¾" WITH NUT & WASHER- HSN CODE 7318 | Nos | 659 | 2020-10-07 12:00 | 2020-10-10 12:00 | 100 | 100 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | PLUMBING NAILS 1½"- HSN CODE 7317 | Kg | 659 | 2020-10-07 12:00 | 2020-10-10 12:00 | 5 | 5 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | UPVC PIPE ( 3MTR ) ¾" ( 20MM )- HSN CODE 3917 | Nos | 660 | 2020-10-07 12:00 | 2020-10-10 12:00 | 100 | 100 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | UPVC ADHESIVE SOLUTION(717) 946 ML- HSN CODE 3917 | Nos | 660 | 2020-10-07 12:00 | 2020-10-10 12:00 | 5 | 5 | 0 | Indrajeet | Completed | For external Facade Plumbing work.
S9 | PERMA DPS WATERPROOFING CHEMICAL-HSN CODE 8424 | Ltr | 661 | 2020-10-10 12:00 | 2020-10-13 12:00 | 25 | 25 | 0 | Indrajeet | Completed | For Waterproofing work on RCC.
S9 | ACRYLIC EXTERIOR EMULSION PAINT- HSN CODE 3209 | Ltr | 662 | 2020-10-10 12:00 | 2020-10-12 12:00 | 4.557 | 4.557 | 0 | Indrajeet | Completed | FOR EXTERNAL PAINTING WORK.
S9 | ACRYLIC EXTERIOR EMULSION PAINT- HSN CODE 3209 | Ltr | 662 | 2020-10-10 12:00 | 2020-10-12 12:00 | 2.8442 | 2.8442 | 0 | Indrajeet | Completed | FOR EXTERNAL PAINTING WORK.
S9 | ACRYLIC EXTERIOR EMULSION PAINT- HSN CODE 3209 | Ltr | 662 | 2020-10-10 12:00 | 2020-10-12 12:00 | 1.9646 | 1.9646 | 0 | Indrajeet | Completed | FOR EXTERNAL PAINTING WORK.
S9 | ACRYLIC EXTERIOR EMULSION PAINT- HSN CODE 3209 | Ltr | 662 | 2020-10-10 12:00 | 2020-10-12 12:00 | 5.7 | 5.7 | 0 | Indrajeet | Completed | FOR EXTERNAL PAINTING WORK.
S9 | ACRYLIC EXTERIOR EMULSION PAINT- HSN CODE 3209 | Ltr | 662 | 2020-10-10 12:00 | 2020-10-12 12:00 | 25.4267 | 25.4267 | 0 | Indrajeet | Completed | FOR EXTERNAL PAINTING WORK.
S9 | EXTERIOR WATER BASED ALKALI PRIMER- HSN CODE 3209 | Ltr | 663 | 2020-10-13 12:00 | 2020-10-14 12:00 | 20.4267 | 20.4267 | 0 | Indrajeet | Completed | For exterior painting work.
S9 | PERMA DPS WATERPROOFING CHEMICAL-HSN CODE 8424 | Ltr | 663 | 2020-10-13 12:00 | 2020-10-14 12:00 | 20 | 20 | 0 | Indrajeet | Completed
S9 | NEONFLEX LED STRIP- HSN CODE 94054090 | Rmt | 664 | 2020-10-13 | 2020-10-15 | 5 | 0 | 0 | Rajendra | Unapproved
S9 | LED STRIP - HSN CODE 94054090 | Mtr | 665 | 2020-10-13 | 2020-10-20 | 5 | 5 | 0 | Rajendra | Completed
S9 | LED DRIVER APV 35-24 (IP42) - HSN CODE 94054090 | Nos | 666 | 2020-10-14 | 2020-10-21 | 2 | 2 | 0 | Rajendra | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 667 | 2020-10-16 12:00 | 2020-10-18 12:00 | 259 | 0 | 0 | Indrajeet | Deleted
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 259 | 259 | 0 | Indrajeet | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 202.6 | 202.6 | 0 | Indrajeet | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 202.6 | 202.6 | 0 | Indrajeet | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 202.6 | 202.6 | 0 | Indrajeet | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 202.6 | 202.6 | 0 | Indrajeet | Completed
S9 | AUTUMN BROWN SATIN FINISH STONE- HSN CODE 2516 | Sqft | 668 | 2020-10-16 12:00 | 2020-10-22 12:00 | 202.6 | 202.6 | 0 | Indrajeet | Completed
S9 | WHITE CEMENT- HSN CODE 25232100 | Kg | 669 | 2020-10-17 12:00 | 2020-10-21 12:00 | 50 | 50 | 0 | Indrajeet | Completed | For rendering work.
S9 | KERAKOLL SUPERFLEX STONE ADHESIVES WHITE- HSN CODE 35069900 | Kg | 670 | 2020-10-19 12:00 | 2020-10-22 12:00 | 15 | 15 | 0 | Indrajeet | Completed | For staircase stone cladding work.
S9 | KERAKOLL SUPERFLEX STONE ADHESIVES WHITE- HSN CODE 35069900 | Kg | 670 | 2020-10-19 12:00 | 2020-10-22 12:00 | 25 | 25 | 0 | Indrajeet | Completed | For staircase stone cladding work.
S9 | GROUT BLACK - HSN CODE 3214 | Kg | 671 | 2020-10-19 12:00 | 2020-10-22 12:00 | 5 | 5 | 0 | Indrajeet | Completed
S9 | OIL PAINT SATIN FINISH - HSN CODE 3208 | Ltr | 672 | 2020-10-22 12:00 | 2020-10-26 12:00 | 50 | 0 | 0 | Indrajeet | Deleted | For shutter plates(MS Fins ) spray painting work.
S9 | THINNER- HSN CODE 38051010 | Ltr | 673 | 2020-10-22 12:00 | 2020-10-26 12:00 | 40 | 40 | 0 | Indrajeet | Completed | For oil painting work.
S9 | BOND IT - HSN CODE 38244090 | Kg | 674 | 2020-10-22 12:00 | 2020-10-26 12:00 | 20 | 20 | 0 | Indrajeet | Completed | For gypsum work at 3rd floor
S9 | UPVC FEMALE ADAPTER BRASS THREADED ¾"(20MM)- HSN CODE 3917 | Nos | 675 | 2020-10-26 12:00 | 2020-10-28 12:00 | 107 | 107 | 0 | Indrajeet | Completed | UPVC Brass FTA
S9 | TEFLON TAPE- HSN CODE 3920 | Nos | 676 | 2020-10-26 12:00 | 2020-10-29 12:00 | 200 | 200 | 0 | Indrajeet | Completed | For facade plumbing work.
S9 | ANTISKID TILE 400MM X 400MM DURATO NATURAL-HSN CODE 69072300 | Sqft | 677 | 2020-10-26 12:00 | 2020-11-04 12:00 | 2200 | 2200 | 0 | Indrajeet | Completed | For terrace flooring
S9 | ANTISKID TILE 400MM X 400MM DURATO NATURAL-HSN CODE 69072300 | Sqft | 677 | 2020-10-26 12:00 | 2020-11-04 12:00 | 77 | 77 | 0 | Indrajeet | Completed | For terrace flooring skirting.
S9 | OIL PAINT SATIN FINISH - HSN CODE 3208 | Ltr | 678 | 2020-10-28 12:00 | 2020-10-30 12:00 | 50 | 50 | 0 | Indrajeet | Completed
S9 | PVC PLAIN BEND 110MM(4")- HSN CODE 3917 | Nos | 679 | 2020-10-30 12:00 | 2020-11-06 12:00 | 15 | 0 | 0 | Indrajeet | Deleted
S9 | GI WALL Z BRACKET 32X50X32X4' LONG(2MM THK)- HSN CODE 7216 | Nos | 680 | 2020-10-31 | 2020-11-02 | 10 | 10 | 0 | Indrajeet | Completed
S9 | PVC ELBOW 40MM(1¼")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 14 | 14 | 0 | Indrajeet | Completed
S9 | RCC HUME PIPE 150MM X 2 MTR NP2- HSN CODE 6810 | Nos | 681 | 2020-10-31 | 2020-11-02 | 12 | 12 | 0 | Indrajeet | Completed
S9 | PVC PLAIN BEND 110MM(4")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 15 | 15 | 0 | Indrajeet | Completed
S9 | PVC PLAIN BEND 75MM(2½")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 10 | 10 | 0 | Indrajeet | Completed
S9 | PVC SWR S/S PIPE 40MM(1¼") X 3MTR- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 2 | 2 | 0 | Indrajeet | Completed
S9 | PVC SWR S/S PIPE 75MM(2½") X 3 MTR- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 6 | 6 | 0 | Indrajeet | Completed
S9 | PVC PLUG BEND 110MM(4")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 10 | 10 | 0 | Indrajeet | Completed
S9 | PVC PLUG BEND 75MM(2½")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 6 | 6 | 0 | Indrajeet | Completed
S9 | PVC SHOE 75MM(2½")- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 10 | 10 | 0 | Indrajeet | Completed
S9 | PVC SWR D/S PIPE 110MM(4") X 3 MTR- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 12 | 12 | 0 | Indrajeet | Completed
S9 | PVC SWR D/S PIPE 75MM(2½") X 3MTR- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 6 | 6 | 0 | Indrajeet | Completed
S9 | PVC SWR S/S PIPE 110MM(4") X 3 MTR- HSN CODE 3917 | Nos | 681 | 2020-10-31 | 2020-11-02 | 12 | 12 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 2"(50MM)- HSN CODE 3917 | Nos | 682 | 2020-10-31 12:00 | 2020-11-02 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC PIPE(3MTR) 2"(50MM)- HSN CODE 3917 | Nos | 682 | 2020-10-31 12:00 | 2020-11-02 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC SOCKET/COUPLING 2"(50MM)- HSN CODE 3917 | Nos | 682 | 2020-10-31 12:00 | 2020-11-02 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | CPVC TEE 15MM(½")- HSN CODE 3917 | Nos | 683 | 2020-10-31 12:00 | 2020-11-02 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 20MM(¾")- HSN CODE 3917 | Nos | 683 | 2020-10-31 12:00 | 2020-11-02 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | CPVC TEE 20MM(¾”)- HSN CODE 3917 | Nos | 683 | 2020-10-31 12:00 | 2020-11-02 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | CPVC BRASS MTA 32MM(1¼")- HSN CODE 3917 | Nos | 683 | 2020-10-31 12:00 | 2020-11-02 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 15MM(½")- HSN CODE 3917 | Nos | 683 | 2020-10-31 12:00 | 2020-11-02 12:00 | 20 | 20 | 0 | Indrajeet | Completed
S9 | CPVC ELBOW 32MM(1¼")- HSN CODE 3917 | Nos | 684 | 2020-10-31 12:00 | 2020-11-02 12:00 | 8 | 8 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER TEE ¾”(20MM) X ½"(15MM)- HSN CODE 3917 | Nos | 685 | 2020-10-31 12:00 | 2020-11-02 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | CPVC TO UPVC TRANSITION BUSHING 1¼"(32MM)- HSN CODE 3917 | Nos | 685 | 2020-10-31 12:00 | 2020-11-02 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | CPVC REDUCER SOCKET ¾” (20MM) X ½"(15MM)- HSN CODE 3917 | Nos | 686 | 2020-10-31 12:00 | 2020-11-02 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | CPVC SOLUTION- HSN CODE 3506 | Ltr | 687 | 2020-10-31 12:00 | 2020-11-02 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | CONCEALED BODY FLUSH VALVE- HSN CODE 84818020 | Nos | 687 | 2020-10-31 12:00 | 2020-11-02 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | GI U CLAMP 2½" WITH NUT & WASHER- HSN CODE 7318 | Nos | 687 | 2020-10-31 12:00 | 2020-11-02 12:00 | 20 | 20 | 0 | Indrajeet | Completed
S9 | GI TEE 4"- HSN CODE 7307 | Nos | 688 | 2020-10-31 12:00 | 2020-11-03 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | GI BARREL NIPPLE 4" X 6"- HSN CODE 7307 | Nos | 689 | 2020-10-31 12:00 | 2020-11-03 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | GI REDUCER SOCKET 4” X 2”- HSN CODE 7307 | Nos | 690 | 2020-10-31 12:00 | 2020-11-03 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | HOLDTITE- HSN CODE 3214 | Kg | 691 | 2020-10-31 12:00 | 2020-11-03 12:00 | 0.2 | 0.2 | 0 | Indrajeet | Completed
S9 | TAG (PLUMBING)- HSN CODE 7303 | Kg | 692 | 2020-10-31 12:00 | 2020-11-03 12:00 | 0.1 | 0.1 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 2"(50MM)- HSN CODE 3917 | Nos | 692 | 2020-10-31 12:00 | 2020-11-03 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC SOCKET/COUPLING 2"(50MM)- HSN CODE 3917 | Nos | 693 | 2020-10-31 12:00 | 2020-11-03 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC PIPE(3MTR) 2"(50MM)- HSN CODE 3917 | Nos | 693 | 2020-10-31 12:00 | 2020-11-03 12:00 | 3 | 3 | 0 | Indrajeet | Completed
S9 | UPVC TEE 2"(50MM)- HSN CODE 3917 | Nos | 694 | 2020-10-31 12:00 | 2020-11-03 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC BALL VALVE 2"(50MM)- HSN CODE 3917 | Nos | 694 | 2020-10-31 12:00 | 2020-11-03 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER TEE 2"(50MM) X 1½"(40MM)- HSN CODE 3917 | Nos | 695 | 2020-10-31 12:00 | 2020-11-03 12:00 | 4 | 4 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER SOCKET 2"(50MM) X 1½"(40MM)- HSN CODE 3917 | Nos | 696 | 2020-10-31 12:00 | 2020-11-03 12:00 | 1 | 1 | 0 | Indrajeet | Completed
S9 | GI U CLAMP 2" WITH NUT & WASHER- HSN CODE 7318 | Nos | 696 | 2020-10-31 12:00 | 2020-11-03 12:00 | 8 | 8 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER TEE 1½"(40MM) X 1¼"(32MM)- HSN CODE 3917 | Nos | 697 | 2020-10-31 12:00 | 2020-11-03 12:00 | 8 | 8 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 1½"(40MM)- HSN CODE 3917 | Nos | 697 | 2020-10-31 12:00 | 2020-11-03 12:00 | 30 | 30 | 0 | Indrajeet | Completed
S9 | UPVC TEE 1¼"(32MM)- HSN CODE 3917 | Nos | 698 | 2020-10-31 12:00 | 2020-11-03 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC TEE 1"(25MM)- HSN CODE 3917 | Nos | 699 | 2020-10-31 12:00 | 2020-11-03 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 1"(25MM)- HSN CODE 3917 | Nos | 699 | 2020-10-31 12:00 | 2020-11-03 12:00 | 12 | 12 | 0 | Indrajeet | Completed
S9 | UPVC BALL VALVE 1¼"(32MM)- HSN CODE 3917 | Nos | 700 | 2020-10-31 12:00 | 2020-11-03 12:00 | 8 | 8 | 0 | Indrajeet | Completed
S9 | UPVC BALL VALVE ¾"(20MM)- HSN CODE 3917 | Nos | 700 | 2020-10-31 12:00 | 2020-11-03 12:00 | 50 | 50 | 0 | Indrajeet | Completed
S9 | UPVC PIPE(3MTR) 1½"(40MM)- HSN CODE 3917 | Nos | 701 | 2020-10-31 12:00 | 2020-11-03 12:00 | 16 | 0 | 0 | Indrajeet | Deleted
S9 | UPVC PIPE(3MTR) 1½"(40MM)- HSN CODE 3917 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 16 | 16 | 0 | Indrajeet | Completed
S9 | UPVC PIPE(3MTR) 1"(25MM)- HSN CODE 3917 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 23 | 23 | 0 | Indrajeet | Completed
S9 | UPVC PIPE ( 3MTR ) 1¼" ( 32MM )- HSN CODE 3917 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 35 | 35 | 0 | Indrajeet | Completed
S9 | GI U CLAMP 1" WITH NUT & WASHER- HSN CODE 7318 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 40 | 40 | 0 | Indrajeet | Completed
S9 | GI U CLAMP 1¼" WITH NUT & WASHER- HSN CODE 7318 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 58 | 58 | 0 | Indrajeet | Completed
S9 | GI U CLAMP 1½" WITH NUT & WASHER- HSN CODE 7318 | Nos | 702 | 2020-10-31 12:00 | 2020-11-03 12:00 | 54 | 54 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER TEE 1¼"(32MM) X ¾”(20MM)- HSN CODE 3917 | Nos | 703 | 2020-10-31 12:00 | 2020-11-03 12:00 | 54 | 54 | 0 | Indrajeet | Completed
S9 | TEFLON TAPE- HSN CODE 3920 | Nos | 703 | 2020-10-31 12:00 | 2020-11-03 12:00 | 250 | 250 | 0 | Indrajeet | Completed
S9 | UPVC END CAP ¾"(20MM)- HSN CODE 3917 | Nos | 703 | 2020-10-31 12:00 | 2020-11-03 12:00 | 8 | 8 | 0 | Indrajeet | Completed
S9 | UPVC ADHESIVE SOLUTION(705) 946 ML- HSN CODE 3917 | Nos | 704 | 2020-10-31 12:00 | 2020-11-03 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC MALE ADAPTER BRASS THREADED 2"(50MM)- HSN CODE 3917 | Nos | 705 | 2020-10-31 12:00 | 2020-11-03 12:00 | 2 | 2 | 0 | Indrajeet | Completed
S9 | UPVC ELBOW 1¼"(32MM)- HSN CODE 3917 | Nos | 706 | 2020-10-31 12:00 | 2020-11-03 12:00 | 24 | 24 | 0 | Indrajeet | Completed
S9 | GI WALL Z BRACKET 32X75X32X4' LONG(2MM THK)- HSN CODE 7216 | Nos | 707 | 2020-10-31 12:00 | 2020-11-03 12:00 | 10 | 10 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER BUSHING 1"(25MM) X ¾"(20MM)- HSN CODE 3917 | Nos | 707 | 2020-10-31 12:00 | 2020-11-03 12:00 | 12 | 12 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER BUSHING 1¼"(32MM) X ¾"(20MM)- HSN CODE 3917 | Nos | 707 | 2020-10-31 12:00 | 2020-11-03 12:00 | 18 | 18 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER BUSHING 1¼"(32MM) X 1"(25MM)- HSN CODE 3917 | Nos | 707 | 2020-10-31 12:00 | 2020-11-03 12:00 | 12 | 12 | 0 | Indrajeet | Completed
S9 | UPVC REDUCER BUSHING 1½"(40MM) X 1"(25MM)- HSN CODE 3917 | Nos | 707 | 2020-10-31 12:00 | 2020-11-03 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | PVC CONDUIT BEND 25MM- HSN CODE 39174000 | Nos | 708 | 2020-10-31 12:00 | 2020-11-02 12:00 | 50 | 50 | 0 | Indrajeet | Completed
S9 | PVC CONDUIT SOCKET 25MM- HSN CODE 39174000 | Nos | 708 | 2020-10-31 12:00 | 2020-11-02 12:00 | 30 | 30 | 0 | Indrajeet | Completed
S9 | COPPER FLEXIBLE CABLE 1.5 SQMM X 3 CORE- HSN CODE 8544 | Rmt | 708 | 2020-10-31 12:00 | 2020-11-02 12:00 | 100 | 100 | 0 | Indrajeet | Completed
S9 | PVC 4 WAY JUNCTION BOX 25MM- HSN CODE 39174000 | Nos | 708 | 2020-10-31 12:00 | 2020-11-02 12:00 | 20 | 20 | 0 | Indrajeet | Completed
S9 | PVC CONDUIT TEE 25MM :- HSN CODE 39174000 | Nos | 709 | 2020-10-31 12:00 | 2020-11-02 12:00 | 15 | 15 | 0 | Indrajeet | Completed
S9 | SELF TAPPING SCREW 1"- HSN CODE 7318 | Nos | 710 | 2020-10-31 12:00 | 2020-11-04 12:00 | 100 | 100 | 0 | Indrajeet | Completed
S9 | ASBESTOS PLAIN SHEET (CEMENT) 8FT X 4FT X12MM- HSN CODE 6811 | Nos | 710 | 2020-10-31 12:00 | 2020-11-04 12:00 | 6 | 6 | 0 | Indrajeet | Completed
S9 | ANTISKID TILE 400MM X 400MM DURATO NATURAL-HSN CODE 69072300 | Sqft | 711 | 2020-10-31 12:00 | 2020-11-04 12:00 | 22 | 22 | 0 | Indrajeet | Completed
S9 | WEBER NOVA GREY - HSN CODE 3824 | Kg | 712 | 2020-10-31 12:00 | 2020-11-04 12:00 | 4500 | 4500 | 0 | Indrajeet | Completed | For terrace tile fixing.
S9 | WATER REPELLENT TRS 500 STONE CHEMICAL- HSN CODE 3824 | Ltr | 713 | 2020-11-03 12:00 | 2020-11-08 12:00 | 40 | 0 | 0 | Satish | Unapproved
S9 | WHITE CEMENT- HSN CODE 25232100 | Kg | 714 | 2020-11-03 12:00 | 2020-11-03 12:00 | 20 | 0 | 0 | Satish | Unapproved