## 1Work_Completion_Browse63740690
| Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse
| Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA
| Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS | Contractor : SAMARTH ELECTRICALS & CONTRACTORS
| From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20 | Total Records: 20 Records 1 to 20
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
MSEB MAIN WIRING OF FLAT (DUCT TO METER ROOM) | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 51 | 1124.55 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
TELEPHONE KRONE BOX FIXING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 950 | 190 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A SEPARATE/FULL PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 34 | 193 | 1312.4 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A HALF PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 86 | 34.4 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
EXHAUST FAN POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 160 | 32 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 35 | 162 | 1134 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 162 | 64.8 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.2 | 24 | 528.96 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
MSEB MAIN WIRING OF FLAT (DUCT TO METER ROOM) | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 51 | 1124.55 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A SEPARATE/FULL PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 34 | 193 | 1312.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A HALF PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 86 | 34.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 35 | 162 | 1134 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 162 | 32.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 24 | 529.2 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 6 | 162 | 194.4 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
2 WAY WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 7 | 270 | 378 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 76 | 162 | 2462.4 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 24 | 529.2 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE CONCEALED WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 75 | 24 | 360 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
VIDEO DOOR PHONE POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 4 | 165 | 132 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS