## 1Work_Completion_Browse63740695
| Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse
| Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA | Project : MANIK SIGNIA
| From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020 | From Date : 11/10/2020 To date: 11/10/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38 | Total Records: 38 Records 1 to 38
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
LAYING & FIXING RCC HUME PIPE - 150MM (6") DIA. | DINESH KUMAR SINGH | 1 | DRAINAGE 150MM DIA. (6") RCC PIPE LINE | 147 | 40 | 5880 | 2020-10-28 17:44 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -5685 | DINESH KUMAR SINGH
FIXING BRASS BALL VALVE -20MM (3/4") | DINESH KUMAR SINGH | 1 | SITE EXPENSES BRASS BALL VALVE | 2 | 100 | 200 | 2020-10-28 17:56 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -11365 | DINESH KUMAR SINGH
LAYING & FIXING GI PIPE LINE - 38MM (1 1/2") DIA. | DINESH KUMAR SINGH | 1 | SITE EXPENSES 38MM DIA (1 1/2") GI LINE | 20 | 50 | 1000 | 2020-10-28 17:56 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -10565 | DINESH KUMAR SINGH
LAYING & FIXING GI PIPE LINE - 20MM (3/4") DIA. | DINESH KUMAR SINGH | 1 | SITE EXPENSES 20MM DIA (3/4") GI LINE | 3 | 25 | 75 | 2020-10-28 17:56 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -11490 | DINESH KUMAR SINGH
CONSTRUCTION OF CHAMBER -3' X 3' (DEPTH UP TO 1200 MM ) | DINESH KUMAR SINGH | 1 | DRAINAGE STORM WATER / DRAINAGE CHAMBER | 1 | 3000 | 3000 | 2020-10-28 17:56 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -8565 | DINESH KUMAR SINGH
LAYING & FIXING PVC PIPE - 100MM (4") DIA. | DINESH KUMAR SINGH | 1 | DRAINAGE PVC PIPE LINE | 47 | 30 | 1410 | 2020-10-28 18:06 | AGAINST RA BILL 100% | 100 |  | 1 | 11565 | 2020-10-31 14:23 | -10155 | DINESH KUMAR SINGH
RCC LABOUR WORK (SLAB HOUSEKEEPING & CLEANING) | UNITED INFRA | 1 | 1ST SLAB RCC M35 CONCRETE (RMC) | 10384.98 | 4 | 41539.92 | 2020-10-31 16:01 | AGAINST RA BILL 100% | 100 |  | 7 | 41539.92 | 2020-11-02 14:02 | 0 | UNITED INFRA
RCC LABOUR WORK (SLAB HOUSEKEEPING & CLEANING) | UNITED INFRA | 1 | 2ND SLAB RCC M35 CONCRETE (RMC) | 7522.92 | 4 | 30091.68 | 2020-10-31 16:38 | AGAINST RA BILL 100% | 100 |  | 8 | 30091.68 | 2020-11-02 14:03 | 0 | UNITED INFRA
RCC LABOUR WORK (SLAB AREA BASIS) | UNITED INFRA | 1 | 4TH SLAB RCC M35 CONCRETE (RMC) | 6508.72 | 142 | 924238.24 | 2020-10-16 16:31 | AGAINST RA BILL 100% | 100 |  | 6 | 924238.24 | 2020-10-31 14:27 | 0 | UNITED INFRA
8MM REBARING WORK | BHAKI CONSTRUCTION | 2 | RCC MISC. WORK REBARING WORK | 25 | 40 | 1000 | 2020-10-27 15:14 | AGAINST RA BILL 100% | 100 |  | 1 | 1000 | 2020-10-29 17:50 | 0 | BHAKI CONSTRUCTION
SECURITY GUARD (NIGHT SHIFT - 12 HRS DUTY) | SECURE SECURITY SERVICES | 3 | HOUSEKEEPING & SAFETY SITE SECURITY SERVICE | 1 | 14200 | 14200 | 2020-10-28 12:22 | AGAINST RA BILL | 100 |  | 3 | 28400 | 2020-10-30 11:39 | -14200 | SECURE SECURITY SERVICES
SECURITY GUARD (DAY SHIFT -12 HRS DUTY) | SECURE SECURITY SERVICES | 3 | HOUSEKEEPING & SAFETY SITE SECURITY SERVICE | 1 | 14200 | 14200 | 2020-10-28 12:22 | AGAINST RA BILL | 100 |  | 3 | 28400 | 2020-10-30 11:39 | -14200 | SECURE SECURITY SERVICES
SECURITY GUARD (NIGHT SHIFT - 12 HRS DUTY) | SECURE SECURITY SERVICES | 3 | HOUSEKEEPING & SAFETY SITE SECURITY SERVICE | 1 | 14200 | 14200 | 2020-11-05 12:42 | AGAINST RA BILL | 100 |  | 4 | 28400 | 2020-11-05 13:40 | -14200 | SECURE SECURITY SERVICES
SECURITY GUARD (NIGHT SHIFT - 12 HRS DUTY) | SECURE SECURITY SERVICES | 3 | HOUSEKEEPING & SAFETY SITE SECURITY SERVICE | 1 | 14200 | 14200 | 2020-11-05 13:07 | AGAINST RA BILL | 100 | [5 empty] | SECURE SECURITY SERVICES
SECURITY GUARD (DAY SHIFT -12 HRS DUTY) | SECURE SECURITY SERVICES | 3 | HOUSEKEEPING & SAFETY SITE SECURITY SERVICE | 1 | 14200 | 14200 | 2020-11-05 13:07 | AGAINST RA BILL | 100 |  | 4 | 28400 | 2020-11-05 13:40 | -14200 | SECURE SECURITY SERVICES
BREAKER ON HIRING BASIS (WITH OPERATOR) | SHETIBA BABAN JADHAV | 4 | PLINTH FLOOR PCC M10-RMC-100MM THK | 3 | 1200 | 3600 | 2020-10-28 17:40 | AGAINST RA BILL | 100 |  | 3 | 30837.5 | 2020-11-04 13:36 | -27237.5 | SHETIBA BABAN JADHAV
EXCAVATION IN SOIL (MANUAL) | SHETIBA BABAN JADHAV | 4 | EARTHWORK & OTHER EXCAVATION IN SOIL | 1495 | 15 | 22425 | 2020-10-28 17:40 | AGAINST RA BILL | 100 |  | 3 | 30837.5 | 2020-11-04 13:36 | -8412.5 | SHETIBA BABAN JADHAV
BACKFILLING WORK (MANUAL) | SHETIBA BABAN JADHAV | 4 | EARTHWORK & OTHER BACK FILLING BY OUTSIDE MATERIAL | 1375 | 3.5 | 4812.5 | 2020-10-28 17:40 | AGAINST RA BILL | 100 |  | 3 | 30837.5 | 2020-11-04 13:36 | -26025 | SHETIBA BABAN JADHAV
MSEB MAIN WIRING OF FLAT (DUCT TO METER ROOM) | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 51 | 1124.55 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
TELEPHONE KRONE BOX FIXING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 950 | 190 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A SEPARATE/FULL PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 34 | 193 | 1312.4 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A HALF PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 86 | 34.4 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
EXHAUST FAN POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 160 | 32 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 35 | 162 | 1134 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 162 | 64.8 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | STILT FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.2 | 24 | 528.96 | 2020-11-09 14:45 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
MSEB MAIN WIRING OF FLAT (DUCT TO METER ROOM) | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 51 | 1124.55 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A SEPARATE/FULL PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 34 | 193 | 1312.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
6A HALF PLUG POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 2 | 86 | 34.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 35 | 162 | 1134 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 1 | 162 | 32.4 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | PARKING FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 24 | 529.2 | 2020-11-09 15:23 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CEILING LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 6 | 162 | 194.4 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
2 WAY WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 7 | 270 | 378 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
WALL LIGHT POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 76 | 162 | 2462.4 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE OPEN DUCT WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 110.25 | 24 | 529.2 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
CAT-6 CABLE CONCEALED WIRING | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 75 | 24 | 360 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS
VIDEO DOOR PHONE POINT | SAMARTH ELECTRICALS & CONTRACTORS | 5 | 01ST FLOOR CONCEALED ELECTRICAL WORK (FLAT & LOBBY) | 4 | 165 | 132 | 2020-11-10 14:35 | SLAB PIPING | 20 | [5 empty] | SAMARTH ELECTRICALS & CONTRACTORS