## 2Work_Completion_Browse63729475
| Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse
| !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!!
| Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All
| Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All
| Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All
| From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010
| Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4 | Page 3 of 4
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 19 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Dhar work | !!Test Contractor | 190 | 01 Internal Plaster 3 - 0 Sq. Mtr._21402 | 20 | 100 | 2000 | 2018-07-21 12:54 | SAMPLE | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 191 | First Floor BBM 115MM (CM 1:4)_22253 | 22 | 12.8 | 281.6 | 2018-07-20 19:12 | SAMPLE | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 193 | First Floor BBM 115MM (CM 1:4)_22253 | 800 | 12.8 | 4096 | 2018-07-23 12:17 | bal.part | 40 |  | 724 | 4096 |  | 0 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 193 | First Floor BBM 115MM (CM 1:4)_22253 | 200 | 12.8 | 1024 | 2018-12-06 12:20 | bal.part | 40 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 193 | First Floor BBM 115MM (CM 1:4)_22253 | 10 | 12.8 | 51.2 | 2019-03-08 10:47 | bal.part | 40 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 193 | First Floor BBM 115MM (CM 1:4)_22253 | 100 | 12.8 | 512 | 2019-03-08 10:48 | bal.part | 40 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 193 | First Floor BBM 115MM (CM 1:4)_22253 | 50 | 12.8 | 256 | 2019-03-01 12:25 | bal.part | 40 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 194 | First Floor BBM 115MM (CM 1:4)_22253 | 100.68 | 12.8 | 773.2224 | 2018-08-22 12:28 | 60part | 60 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 194 | First Floor BBM 115MM (CM 1:4)_22253 | 200.6 | 12.8 | 1027.072 | 2018-08-22 12:28 | bal.part | 40 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 196 | First Floor BBM 115MM (CM 1:4)_22253 | 1000 | 12.8 | 7680 | 2018-08-22 12:28 | 60part | 60 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 196 | First Floor BBM 115MM (CM 1:4)_22253 | 800 | 12.8 | 4096 | 2018-07-23 14:00 | bal.part | 40 |  | 725 | 4096 |  | 0 | !!Test Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 197 | Raghvendra Task Tax Rate Test_103506 | 50 | 100 | 3000 | 2018-08-18 11:13 | 60part | 60 |  | 735 | 3000 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 197 | Raghvendra Task Tax Rate Test_103506 | 50 | 100 | 3000 | 2018-08-20 09:50 | 60part | 60 |  | 736 | 3000 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 197 | Raghvendra Task Tax Rate Test_103506 | 0 | 100 | 0 | 2018-08-21 16:54 | bal.part | 40 | [5 empty] | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 197 | Raghvendra Task Tax Rate Test_103506 | 30 | 100 | 1200 | 2018-08-20 09:50 | bal.part | 40 |  | 745 | 1200 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 197 | Raghvendra Task Tax Rate Test_103506 | 70 | 100 | 2800 | 2018-08-18 11:13 | bal.part | 40 |  | 744 | 2800 |  | 0 | ! Dinkar Contractor
Internal Plaster | ! Dinkar Contractor | 198 | 01 Internal Plaster_17659 | 100 | 42 | 3360 | 2018-09-25 17:39 | work Comp-stage1 | 80 |  | 740 | 4200 |  | -840 | ! Dinkar Contractor
Internal Plaster | ! Dinkar Contractor | 198 | 01 Internal Plaster_17659 | 100 | 42 | 840 | 2018-09-25 17:39 | work Comp-stage2 | 20 |  | 740 | 4200 |  | -3360 | ! Dinkar Contractor
BBM Labour Work | !!Test Contractor | 199 | First Floor BBM 115MM (CM 1:4)_22253 | 100 | 1000 | 100000 | 2019-02-11 | SAMPLE | 100 |  | 815 | 100000 | 2020-01-27 15:03 | 0 | !!Test Contractor
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 3.0771 | 11 | 16.9241 | 2017-05-24 13:12 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 2.344 | 11 | 12.892 | 2017-02-04 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 2.3444 | 11 | 12.8942 | 2017-02-04 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:50 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:51 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:05 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 1 | 11 | 5.5 | 2016-09-06 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:05 | 100%Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:51 | 100%Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:51 | 100%Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 2 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | 100%Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 1000 | 4500 | 1125000 | 2016-08-22 18:15 | While generate WO | 25 |  | 567 | 1125000 |  | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 1000 | 4500 | 3375000 | 2016-08-22 18:15 | On Completion | 75 |  | 568 | 3375000 |  | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 20 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 4500 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 15 | 300 | 1125 | 2016-08-22 18:15 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 15 | 300 | 3375 | 2016-08-22 18:15 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 20 | RCC RCC COLUMN M20_21941 | 0 | 300 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75075 | 1.5497 | 15 | 13.9473 | 2018-11-22 11:34 | 60part | 60 |  | 746 | 199.67 |  | -185.7227 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75075 | 1.5497 | 15 | 9.2982 | 2018-11-22 11:34 | bal.part | 40 |  | 746 | 199.67 |  | -190.3718 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75035 | 5.2252 | 15 | 78.378 | 2018-11-22 11:34 | SAMPLE | 100 |  | 746 | 199.67 |  | -121.292 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75036 | 5.2252 | 15 | 78.378 | 2018-11-22 11:34 | SAMPLE | 100 |  | 746 | 199.67 |  | -121.292 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75036 | 0.6556 | 15 | 9.834 | 2018-11-22 11:34 | Full Completion Payment 100 | 100 |  | 746 | 199.67 |  | -189.836 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75035 | 0.6556 | 15 | 9.834 | 2018-11-22 11:34 | Full Completion Payment 100 | 100 |  | 746 | 199.67 |  | -189.836 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 200 | First Floor BBM 115MM (CM 1:4)_75035 | 0 | 15 | 0 | 2018-12-05 14:08 | Full Completion Payment 100 | 100 | [5 empty] | !!Test Contractor
All LAbour | ! Dinkar Contractor | 201 | Painting Cement Work_745383 | 1 | 20 | 20 | 2018-12-14 | SAMPLE | 100 |  | 748 | 520 | 2018-12-19 17:21 | -500 | ! Dinkar Contractor
All LAbour | ! Dinkar Contractor | 201 | Painting Cement Work_745383 | 1 | 20 | 20 | 2018-12-14 | SAMPLE | 100 |  | 747 | 770 | 2018-12-14 15:07 | -750 | ! Dinkar Contractor
All LAbour | ! Dinkar Contractor | 201 | Painting Cement Work_745383 | 0.3158 | 20 | 6.316 | 2019-01-30 | SAMPLE | 100 |  | 779 | 6.32 |  | -0.004 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 30.5 | 100 | 1830 | 2019-01-30 | 60part | 60 |  | 781 | 1830 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 12.5 | 100 | 750 | 2018-12-14 | 60part | 60 |  | 747 | 770 | 2018-12-14 15:07 | -20 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 5 | 100 | 300 | 2018-12-21 | 60part | 60 |  | 777 | 300 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 2 | 100 | 120 | 2018-12-21 | 60part | 60 |  | 780 | 120 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 3 | 100 | 120 | 2018-12-21 | bal.part | 40 |  | 782 | 120 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 4 | 100 | 160 | 2018-12-21 | bal.part | 40 |  | 784 | 160 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 12.5 | 100 | 500 | 2018-12-14 | bal.part | 40 |  | 748 | 520 | 2018-12-19 17:21 | -20 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra Task Tax Rate Test_105494 | 30.5 | 100 | 1220 | 2019-01-30 | bal.part | 40 |  | 785 | 1220 |  | 0 | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra 00 SAKARIYA finishing_22071 | 100 | 0 | 0 | 2019-01-03 15:43 | 60part | 60 | Entry from Task Closure screen |  |  |  |  | ! Dinkar Contractor
Brickwork Tax Rate Test | ! Dinkar Contractor | 201 | Raghvendra 00 SAKARIYA finishing_22071 | 100 | 0 | 0 | 2019-01-03 15:43 | bal.part | 40 | Entry from Task Closure screen |  |  |  |  | ! Dinkar Contractor
BBM Labour Work | !!Test Contractor | 202 | First Floor BBM 115MM (CM 1:4)_105034 | 0.3311 | 15 | 2.9799 | 2019-01-30 | 60part | 60 |  | 813 | 4.97 | 2020-01-23 15:22 | -1.9901 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 202 | First Floor BBM 115MM (CM 1:4)_105034 | 0.3311 | 15 | 1.9866 | 2019-01-30 | bal.part | 40 |  | 813 | 4.97 | 2020-01-23 15:22 | -2.9834 | !!Test Contractor
Test feb 2019 labour | Test feb 2019 | 204 | Test feb 2019 WBS Group Test 2019 feb task | 4 | 450 | 1080 | 2019-02-01 | 60part | 60 |  | 749 | 67500 | 2019-02-02 15:54 | -66420 | Test feb 2019
Test feb 2019 labour | Test feb 2019 | 204 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 450 | 270 | 2019-08-03 11:35 | 60part | 60 | [5 empty] | Test feb 2019
Test feb 2019 labour | Test feb 2019 | 204 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 450 | 270 | 2019-10-05 | 60part | 60 | [5 empty] | Test feb 2019
Test feb 2019 labour | Test feb 2019 | 204 | Test feb 2019 WBS Group Test 2019 feb task | 150 | 450 | 27000 | 2019-02-01 | bal.part | 40 |  | 749 | 67500 | 2019-02-02 15:54 | -40500 | Test feb 2019
Internal Plaster | ! Dinkar Contractor | 207 | 01 Internal Plaster_17659 | 2 | 42 | 84 | 2019-02-27 10:04 | final | 100 |  | 821 | 294 |  | -210 | ! Dinkar Contractor
Internal Plaster | ! Dinkar Contractor | 207 | 01 Internal Plaster_17659 | 5 | 42 | 210 | 2019-02-27 10:06 | final | 100 |  | 821 | 294 |  | -84 | ! Dinkar Contractor
Test QA labor | Test feb 2019 contractor | 208 | Test QA WBS Group Test QA cementing task | 50 | 400 | 12000 | 2019-03-06 15:00 | 60part | 60 |  | 751 | 12000 | 2019-03-06 15:34 | 0 | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 208 | Test QA WBS Group Test QA cementing task | 50 | 400 | 8000 | 2019-03-06 15:00 | bal.part | 40 | [5 empty] | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 208 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 20 | 20 | 2020-03-02 17:26 | final | 100 | [5 empty] | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 209 | Test QA WBS Group Test QA cementing task | 50 | 400 | 12000 | 2019-03-06 15:37 | 60part | 60 |  | 752 | 20000 |  | -8000 | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 209 | Test QA WBS Group Test QA cementing task | 50 | 400 | 8000 | 2019-03-06 15:37 | bal.part | 40 |  | 752 | 20000 |  | -12000 | Test feb 2019 contractor
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 21 | For Account Linking BBM 115MM (CM 1:4)_21793 | 1000 | 4500 | 1125000 | 2016-08-24 12:31 | While generate WO | 25 |  | 570 | 4504500 | 2016-08-24 13:10 | -3379500 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 21 | For Account Linking BBM 115MM (CM 1:4)_21793 | 1000 | 4500 | 3375000 | 2016-08-24 12:31 | On Completion | 75 |  | 570 | 4504500 | 2016-08-24 13:10 | -1129500 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 21 | RCC RCC COLUMN M20_21941 | 15 | 300 | 1125 | 2016-08-24 12:31 | While generate WO | 25 |  | 570 | 4504500 | 2016-08-24 13:10 | -4503375 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 21 | RCC RCC COLUMN M20_21941 | 15 | 300 | 3375 | 2016-08-24 12:31 | On Completion | 75 |  | 570 | 4504500 | 2016-08-24 13:10 | -4501125 | 01 ABHIJIT CONSTRUCTION
Test QA labor | Test feb 2019 contractor | 210 | Test QA WBS Group Test QA cementing task | 10 | 400 | 2400 | 2019-03-06 15:39 | 60part | 60 |  | 753 | 4000 |  | -1600 | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 210 | Test QA WBS Group Test QA cementing task | 10 | 400 | 1600 | 2019-03-06 15:39 | bal.part | 40 |  | 753 | 4000 |  | -2400 | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 211 | Test QA WBS Group Test QA cementing task | 1499994.5 | 400 | 359998680 | 2019-04-01 | 60part | 60 | [5 empty] | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 211 | Test QA WBS Group Test QA cementing task | 2999989 | 400 | 719997360 | 2019-04-01 | 60part | 60 |  | 760 | 719997360 |  | 0 | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 211 | Test QA WBS Group Test QA cementing task | 2999989 | 400 | 479998240 | 2019-04-01 | bal.part | 40 | [5 empty] | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 211 | Test QA WBS Group Test QA cementing task | 1499994.5 | 400 | 239999120 | 2019-04-01 | bal.part | 40 | [5 empty] | Test feb 2019 contractor
Test QA labor | Test feb 2019 contractor | 214 | Test feb 2019 WBS Group Test 2019 feb task | 1.5 | 400 | 360 | 2019-04-02 | 60part | 60 | [5 empty] | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 214 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 20 | 12 | 2020-03-02 17:26 | 60part | 60 | [5 empty] | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 214 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 20 | 12 | 2020-03-02 17:26 | 60part | 60 | [5 empty] | Test feb 2019 contractor
01 Test Brickwork Labour | Test March 19 Contractor | 217 | Test March 19 Brickwork WBS 01 Test Brickwork-(Inches) | 50 | 270 | 13500 | 2019-03-19 | final | 100 |  | 754 | 13500 |  | 0 | Test March 19 Contractor
01 Test Brickwork Labour | Test March 19 Contractor | 217 | Test March 19 Brickwork WBS 01 Test Brickwork-(Inches) | 50 | 270 | 13500 | 2019-03-19 | final | 100 | [5 empty] | Test March 19 Contractor
01 Test Brickwork Labour | Test March 19 Contractor | 217 | Test March 19 Brickwork WBS 01 Test Brickwork-(Inches) | 50 | 270 | 13500 | 2019-03-20 | final | 100 | [5 empty] | Test March 19 Contractor
01 Test Brickwork Labour | Test March 19 Contractor | 217 | Test March 19 Brickwork WBS 01 Test Brickwork-(Inches) | 25 | 270 | 6750 | 2019-03-20 | final | 100 |  | 755 | 6750 | 2019-03-20 14:09 | 0 | Test March 19 Contractor
01 Test Brickwork Labour | Test March 19 Contractor | 217 | Test March 19 Brickwork WBS 01 Test Brickwork-(Inches) | 25 | 270 | 6750 | 2019-03-20 | final | 100 |  | 756 | 6750 |  | 0 | Test March 19 Contractor
Brickwork Labour Pro | Test March 19 Contractor | 218 | Test March 19 Brickwork WBS-- 04 Test Brickwork-(Inches) | 25 | 480 | 12000 | 2019-03-20 | final | 100 |  | 757 | 12000 |  | 0 | Test March 19 Contractor
Brickwork Labour Pro | Test March 19 Contractor | 218 | Test March 19 Brickwork WBS-- 04 Test Brickwork-(Inches) | 25 | 270 | 6750 | 2019-03-20 | final | 100 |  | 758 | 6750 |  | 0 | Test March 19 Contractor
Brickwork Labour Pro | Test March 19 Contractor | 218 | Test March 19 Brickwork WBS-- 04 Test Brickwork-(Inches) | 1 | 270 | 270 | 2019-08-03 11:03 | final | 100 | [5 empty] | Test March 19 Contractor
Brickwork Labour Pro | Test March 19 Contractor | 218 | Test March 19 Brickwork WBS-- 04 Test Brickwork-(Inches) | 1 | 270 | 270 | 2019-08-03 11:58 | final | 100 | [5 empty] | Test March 19 Contractor
Test feb 2019 labour | Test feb 2019 contractor | 219 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 20 | 12 | 2020-03-02 17:26 | 60part | 60 | [5 empty] | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 219 | Test feb 2019 WBS Group Test 2019 feb task | 1 | 20 | 20 | 2020-03-02 17:26 | final | 100 | [5 empty] | Test feb 2019 contractor
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 22 | For Account Linking BBM 115MM (CM 1:4)_21793 | 15 | 250 | 937.5 | 2016-08-25 10:24 | While generate WO | 25 |  | 571 | 4200 | 2016-08-25 12:24 | -3262.5 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 22 | For Account Linking BBM 115MM (CM 1:4)_21793 | 15 | 250 | 2812.5 | 2016-08-25 10:24 | On Completion | 75 |  | 571 | 4200 | 2016-08-25 12:24 | -1387.5 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 22 | RCC RCC COLUMN M20_21941 | 30 | 15 | 112.5 | 2016-08-25 10:24 | While generate WO | 25 |  | 571 | 4200 | 2016-08-25 12:24 | -4087.5 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 22 | RCC RCC COLUMN M20_21941 | 30 | 15 | 337.5 | 2016-08-25 10:24 | On Completion | 75 |  | 571 | 4200 | 2016-08-25 12:24 | -3862.5 | 01 ABHIJIT CONSTRUCTION
SHUTTERING WORK | !!Test Contractor | 224 | BUILDING SHUTTERING WORK_74523 | 0.1111 | 1000 | 111.1 | 2020-01-23 15:50 | final | 100 |  | 814 | 111.1 | 2020-01-23 16:01 | 0 | !!Test Contractor
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 23 | For Account Linking BBM 115MM (CM 1:4)_21793 | 37.5 | 250 | 2343.75 | 2016-08-25 13:12 | While generate WO | 25 |  | 576 | 9375 |  | -7031.25 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 23 | For Account Linking BBM 115MM (CM 1:4)_21793 | 37.5 | 250 | 7031.25 | 2016-08-25 13:12 | On Completion | 75 |  | 576 | 9375 |  | -2343.75 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 23 | RCC RCC COLUMN M20_21941 | 15 | 15 | 56.25 | 2016-08-25 13:12 | While generate WO | 25 |  | 577 | 56.25 |  | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 23 | RCC RCC COLUMN M20_21941 | 15 | 15 | 168.75 | 2016-08-25 13:12 | On Completion | 75 |  | 492 | 75000 |  | -74831.25 | 01 ABHIJIT CONSTRUCTION
Test feb 2019 labour | Test feb 2019 contractor | 231 | Test feb 2019 WBS Group Test 2019 feb task | 2 | 20 | 40 | 2019-05-14 | final | 100 |  | 769 | 40 |  | 0 | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 231 | Test feb 2019 WBS Group Test 2019 feb task | 1.25 | 20 | 25 | 2019-05-14 | final | 100 |  | 770 | 25 |  | 0 | Test feb 2019 contractor
Test feb 2019 labour | Test feb 2019 contractor | 231 | Test feb 2019 WBS Group Test 2019 feb task | 1.5 | 20 | 30 | 2019-05-14 | final | 100 |  | 771 | 30 |  | 0 | Test feb 2019 contractor
2106Labour | ! Dinkar Contractor | 236 | june 2106Task | 100 | 100 | 10000 | 2019-06-21 | Full Completion Payment 100 | 100 |  | 772 | 10000 | 2019-06-21 17:19 | 0 | ! Dinkar Contractor
pranav test labor | Test advance contractor | 238 | test3 IN SOFT ROCK_102677 | 0.5 | 10 | 5 | 2019-06-26 | final | 100 | [5 empty] | Test advance contractor
pranav test labor | Test advance contractor | 238 | test3 IN SOFT ROCK_102677 | 0.2 | 10 | 2 | 2019-07-06 | final | 100 | [5 empty] | Test advance contractor
pranav test labor | Test advance contractor | 238 | test3 IN SOFT ROCK_102677 | 0.3 | 10 | 3 | 2019-08-05 16:38 | final | 100 | [5 empty] | Test advance contractor
All LAbour | ! Dinkar Contractor | 239 | CEMENT Cement Work_74539 | 2 | 200 | 400 | 2019-10-04 11:19 | final | 100 | test |  |  |  |  | ! Dinkar Contractor
All LAbour | ! Dinkar Contractor | 239 | CEMENT Cement Work_74539 | 2 | 200 | 400 | 2019-10-04 11:29 | final | 100 | test |  |  |  |  | ! Dinkar Contractor
pranav test labor | ! Dinkar Contractor | 243 | pranav MB test Wall Building | 3.75 | 100 | 375 | 2019-08-29 17:41 | final | 100 | [5 empty] | !!Sample Contractor
pranav test labor | ! Dinkar Contractor | 243 | pranav MB test Wall Building | 0.5 | 100 | 50 | 2020-02-05 10:47 | final | 100 | [5 empty] | ! Dinkar Contractor
pranav test labor | ! Dinkar Contractor | 243 | pranav MB test Wall Building | 0 | 100 | 0 | 2020-02-11 15:25 | final | 100 |  | 817 | 0 |  | 0 | ! Dinkar Contractor
pranav test labor | ! Dinkar Contractor | 243 | pranav MB test Wall Building | 0 | 100 | 0 | 2020-02-11 15:28 | final | 100 |  | 817 | 0 |  | 0 | ! Dinkar Contractor
pranav test labor | ! Dinkar Contractor | 243 | pranav MB test Wall Building | 0 | 100 | 0 | 2020-02-11 15:29 | final | 100 |  | 817 | 0 |  | 0 | ! Dinkar Contractor
pranav test labor | !!Sample Contractor | 244 | pranav MB test Wall Building | 0.12 | 110 | 13.2 | 2020-02-05 16:41 | final | 100 |  | 820 | 63 |  | -49.8 | !!Sample Contractor
pranav test labor | !!Sample Contractor | 244 | pranav MB test Wall Building | 2 | 110 | 220 | 2020-02-05 16:41 | final | 100 | [5 empty] | !!Sample Contractor
pranav test labor | !!Sample Contractor | 244 | pranav MB test Wall Building | 3 | 110 | 330 | 2019-08-29 17:49 | final | 100 |  | 778 | 330 | 2019-10-11 18:03 | 0 | ! Dinkar Contractor
BBM 3rd floor | ! Dinkar Contractor | 245 | Budget Test Group BBM 8" Thk. | 1 | 100 | 100 | 2019-11-05 10:49 | final | 100 |  | 800 | 100 |  | 0 | ! Dinkar Contractor
A_Swa | ! Dinkar Contractor | 248 | A BUILDING_22069 01 Internal Plaster-(Cu.Cm) | 1 | 10 | 6 | 2020-01-01 17:04 | 60part | 60 | [5 empty] | ! Dinkar Contractor
A_Swa | ! Dinkar Contractor | 248 | A BUILDING_22069 01 Internal Plaster-(Cu.Cm) | 1 | 10 | 4 | 2020-01-01 17:04 | bal.part | 40 | [5 empty] | ! Dinkar Contractor
Brick work working | 01 ABHIJIT CONSTRUCTION | 25 | BrickWork Brickwork | 60 | 4500 | 67500 | 2016-08-27 10:55 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 25 | BrickWork Brickwork | 10 | 4500 | 11250 | 2017-06-21 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 25 | BrickWork Brickwork | 30 | 4500 | 33750 | 2019-02-21 16:17 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 25 | BrickWork Brickwork | 60 | 4500 | 202500 | 2016-08-27 10:55 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 25 | RCC RCC COLUMN M20_21941 | 30 | 300 | 2250 | 2016-08-27 10:55 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 25 | RCC RCC COLUMN M20_21941 | 30 | 300 | 6750 | 2016-08-27 10:55 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 27 | 01 Internal Plaster_17658 | 25 | 100 | 2500 | 2016-08-30 | As per work Completion | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 27 | 01 Internal Plaster_17658 | 25 | 100 | 2500 | 2016-08-31 | As per work Completion | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 28 | BBM 115MM (CM 1:4)_21791 | 10 | 250 | 625 | 2016-09-03 10:20 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 28 | BBM 115MM (CM 1:4)_21791 | 10 | 250 | 1875 | 2016-09-03 10:20 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 28 | RCC RCC COLUMN M20_21941 | 15000 | 300 | 1125000 | 2016-09-03 10:20 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 28 | RCC RCC COLUMN M20_21941 | 15000 | 300 | 3375000 | 2016-09-03 10:20 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 29 | BBM 115MM (CM 1:4)_21791 | 0.4 | 4500 | 450 | 2016-09-06 15:09 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 29 | BBM 115MM (CM 1:4)_21791 | 0.4 | 4500 | 1350 | 2016-09-06 15:09 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 29 | RCC RCC COLUMN M20_21941 | 10 | 300 | 750 | 2016-09-06 15:09 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 29 | RCC RCC COLUMN M20_21941 | 10 | 300 | 2250 | 2016-09-06 15:09 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 3 | BBM 115MM (CM 1:4)_21791 | 50 | 250 | 11625 | 2016-07-20 | AGAINST COMPLETION OF WORK | 93 |  | 496 | 11625 | 2016-07-29 19:46 | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 3 | BBM 115MM (CM 1:4)_21791 | 50 | 250 | 11625 | 2016-07-20 16:58 | AGAINST COMPLETION OF WORK | 93 |  | 500 | 11625 | 2017-09-04 16:36 | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 3 | BBM 115MM (CM 1:4)_21791 | 40 | 250 | 700 | 2016-07-20 16:58 | RETENTION | 7 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 33 | RCC RCC COLUMN M20_21941 | 0.5 | 6667 | 833.375 | 2016-09-06 15:43 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 33 | RCC RCC COLUMN M20_21941 | 0.5 | 6667 | 2500.125 | 2016-09-06 15:43 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 34 | RCC RCC COLUMN M20_21941 | 1 | 6667 | 1666.75 | 2016-09-07 10:23 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 34 | RCC RCC COLUMN M20_21941 | 1 | 6667 | 5000.25 | 2016-09-07 10:23 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 35 | RCC RCC COLUMN M20_21941 | 0.5 | 6667 | 833.375 | 2016-09-08 10:24 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 35 | RCC RCC COLUMN M20_21941 | 0.5 | 6667 | 2500.125 | 2016-09-08 10:24 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 36 | BBM 115MM (CM 1:4)_21791 | 5 | 4500 | 5625 | 2016-09-08 12:44 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 36 | BBM 115MM (CM 1:4)_21791 | 5 | 4500 | 16875 | 2016-09-08 12:44 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 36 | RCC RCC COLUMN M20_21941 | 100 | 300 | 7500 | 2016-09-08 12:44 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 36 | RCC RCC COLUMN M20_21941 | 100 | 300 | 22500 | 2016-09-08 12:44 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 37 | BBM 115MM (CM 1:4)_21791 | 2 | 4500 | 2250 | 2016-09-08 16:11 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 37 | BBM 115MM (CM 1:4)_21791 | 2 | 4500 | 6750 | 2016-09-08 16:11 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 37 | RCC RCC COLUMN M20_21941 | 100 | 300 | 7500 | 2016-09-08 16:11 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 37 | RCC RCC COLUMN M20_21941 | 100 | 300 | 22500 | 2016-09-08 16:11 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 38 | 01 Internal Plaster 1_17657 | 100 | 100 | 2500 | 2016-09-14 14:11 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 38 | 01 Internal Plaster 1_17657 | 100 | 100 | 7500 | 2016-09-14 14:11 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 39 | RCC RCC COLUMN M20_21941 | 5 | 6667 | 8333.75 | 2016-09-16 17:39 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | AA Contractors | 4 | BBM 115MM (CM 1:4)_21791 | 0 | 1000 | 0 | 2016-11-19 15:49 | Full Completion Payment 100 | 100 | [5 empty] | AA Contractors